## Metric Tracker
| TERM TWO | [5 empty] | EASTER BREAK |  |  |  | TERM THREE
QA Metric Tracker |  |  | Iteration 1 (20th Feb - 5th Mar) |  |  |  | Iteration 3 (19th Mar - 2nd Apr) |  |  |  | Iteration 5 (16th Apr - 30th Apr) |  |  |  | Iteration 7 (14th May - 28th May) |  |  | Project Deadline
[5 empty] | Iteration 2 (5th Mar - 19th Mar) |  |  |  | Iteration 4 (2nd Apr - 16th Apr) |  |  |  | Iteration 6 (30th Apr - 14th May)
2019 / 2020 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Break 1 | Break 2 | Break 3 | Break 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Week Commencing: | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15
Project Manager
Work Efficiency | 2020-03-02: 8.55; 2020-03-16: 8.38; 2020-03-30: 9.39; 2020-04-13: 13.25; 2020-04-27: 10.1; 2020-05-11: 0; 2020-05-25: 0
Team Productivity |  |  |  | 11.14 | 10.82 | 11.25 | 5.71 | 6.32 | 12.86 | 13.18 | 15.5 | 10.46 | 16.18 | 12.04 | 8.07 | 14.71 | 17.46
Team Contentment | 2020-03-02: 62.5%; 2020-03-16: 87.5%; 2020-03-30: 75%; 2020-04-13: 100%; 2020-04-27: 87.5%; 2020-05-11: 87.5%
Reachable Project Scope | 2020-03-02: 91%; 2020-03-16: 28%; 2020-03-30: 84%; 2020-04-13: 76%; 2020-04-27: 67%; 2020-05-11: 100%; 2020-05-25: 100%
Client Satisfaction | 2020-03-02: 70%; 2020-03-16: 75%; 2020-03-30: 80%; 2020-04-13: 50%; 2020-04-27: 80%; 2020-05-11: 90%; 2020-05-25: 95%
Finance Manager
Percentage Iteration Progress Expenditure |  |  |  |  | -15% | -13% | -8% | -37% | -40% | -33% | 10% | 15% | 20% | 85% | 75% | 42% | 42%
Labour Buffer |  |  |  | 1.5 | 6.75 | 15.25 | 32.5 | 72 | 67.25 | 42 | 36 | -6 | -40 | -27.2 | -31 | -24 | -117
Development Cost Difference | 2020-03-02: -246.88; 2020-03-16: -534.38; 2020-03-30: 140.63; 2020-04-13: 525; 2020-04-27: 184.38; 2020-05-11: -681.25; 2020-05-25: -762.5
Marketing Manager
Profile Visits |  |  |  | 22 | 56 | 179 | 337 | 380 | 429 | 493 | 521 | 558 | 582 | 613 | 662 | 712 | 738
Profile Reach |  |  |  | 5 | 35 | 149 | 250 | 628 | 654 | 735 | 956 | 1163 | 1254 | 1268 | 1465 | 1674 | 1755
Product Growth |  |  |  | 15 | 22 | 63 | 121 | 155 | 165 | 181 | 192 | 197 | 212 | 225 | 240 | 255 | 264
Product Demand | 2020-03-02: 34%; 2020-05-18: 72%
Technical Managers
Software Development Team Agility | 2020-03-02: 29; 2020-03-16: 27; 2020-03-30: 22; 2020-04-13: 74; 2020-04-27: 74; 2020-05-11: 74
Time Estimates for User Stories |  |  |  | -10 | 19.75 | 108 | 132 | 88 | 136 | 134 | 100 | 82 | 68.5 | 109.5 | 109.5 | 23 | 20
Non-Compliance for Coding Standards | 2020-02-24: 2000; 2020-03-02: 826; 2020-03-16: 10; 2020-03-30: 20; 2020-04-13: 30; 2020-04-27: 20; 2020-05-11: 42; 2020-05-25: 100
Design and Specification Manager
User Experience Satisfaction | 2020-03-16: 0; 2020-03-30: 0; 2020-04-13: 0; 2020-04-27: 2; 2020-05-11: 3; 2020-05-25: 4
Similarity to Design Vision |  |  |  |  | -2 | 1 | 0 | 2 | 0 | 0 | -3 | 0 | 0 | -1 | 0 | 1 | 2
Complementation to Project Vision |  |  |  | 5 | 7 | 1 | 1 | 2 | 3 | 1 | 0 | 2 | 0 | 1 | 0 | 1 | 0
Quality Assurance Managers
Coherence to Management QA Metrics |  |  |  | 100% | 95% | 100% | 95% | 100% | 95% | 100% | 95% | 100% | 100% | 100% | 100% | 100% | 100%
Employee Comprehension of Company Ethos | 2020-03-02: 100%; 2020-03-30: 100%; 2020-04-27: 100%
Document Standardisation | 2020-03-02: 7; 2020-03-30: 3; 2020-04-27: 5; 2020-05-25: 2
Testing and Integration Managers
Quality of Code | 2020-03-02: 9; 2020-03-16: 1; 2020-03-30: 9; 2020-04-13: 5; 2020-04-27: 12; 2020-05-11: 3; 2020-05-25: 4
Quality of Tests | 2020-03-02: 9; 2020-03-16: 0; 2020-03-30: 6; 2020-04-13: 0; 2020-04-27: 5; 2020-05-11: 0; 2020-05-25: 1
User Story Integration Latency | 2020-03-02: 5; 2020-03-16: 5; 2020-03-30: 3; 2020-04-13: 4; 2020-04-27: 5; 2020-05-11: 3; 2020-05-25: 3