## Finance Report I
Finance Report I - 21/02/2020
Project Budget:
|  | Budget | Current Expenditure | Predicted Expenditure | Remaining Budget | Predicted Remaining
Overhead Expenditure
| Office Rent | 24042.6 | 12654 | 24042.6 | 11388.6 | 0
| Office Bills and Utilities | 1900 | 1000 | 1900 | 900 | 0
| IT Infrastructure | 3800 | 2000 | 3800 | 1800 | 0
| Contracts | 4000 | 0 | 4000 | 4000 | 0
| Loan Repayments | 1646.0592 | 0 | 1646.0592 | 1646.0592 | 0
Variable Expenditure
| Wages | 18890.625 | 5840.625 | 18890.625 | 13050 | 0
| Overhead | 35388.6592 | 15654 | 35388.6592 | 19734.6592 | 0
| Variable | 19611.3408 | 5840.625 | 18890.625 | 13770.7158 | 720.7158
| Total Injection | 55000 | 21494.625 | 54279.2842 | 33505.375 | 720.7158
| Overhead Recovery Rate (£/hr) | 23.4168 | 10.3583 | 23.4168
Project Cashflow:
| CASHFLOW SUPPORTING DOCUMENT | TERM ONE | [9 empty] | CHRISTMAS BREAK |  |  |  | TERM TWO | [9 empty] | EASTER BREAK |  |  |  | TERM THREE | [9 empty] | TOTAL
| (CF 2019/2020) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Break 1 | Break 2 | Break 3 | Break 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Break 1 | Break 2 | Break 3 | Break 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
| Week Commencing | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-08
Salaries / hrs | bar: TERM ONE Week 1
| Daniel Bishop | 0 | 0 | 0 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2.5 | 5 | 2 | 4 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
| Oliver Clarke | 0 | 0 | 0 | 1 | 1.5 | 1 | 0 | 3.5 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5.5 | 6.25 | 13 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.5
| James Gardner | 0 | 0 | 1 | 3 | 1.5 | 2.25 | 3.25 | 4 | 9.75 | 6.25 | 0 | 0 | 0 | 0 | 0 | 8.5 | 9.5 | 16.5 | 19 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
| Stijn Marynissen | 0 | 0 | 0 | 1 | 1 | 4 | 1 | 3 | 1.75 | 4.75 | 0 | 0 | 0 | 0 | 0 | 9 | 8.25 | 8.5 | 15 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.25
| Che McKirgan | 0 | 0 | 0 | 1 | 1.5 | 3.75 | 1 | 2.25 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 3.5 | 9 | 11.5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.5
| Cameron Smith | 0 | 0 | 0 | 1 | 1.5 | 8 | 4.5 | 7.5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 6 | 4.75 | 7 | 12 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.25
| Oliver Still | 0 | 0 | 0 | 1 | 3 | 1 | 2.5 | 3 | 9.5 | 4.75 | 0 | 0 | 0 | 0 | 0 | 15.5 | 17.25 | 8.5 | 18 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.5
| Eric Walker | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1.5 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 3.25 | 3.5 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.25
Expenses / £ | bar: TERM ONE Week 1
| Wages | 0 | 0 | 12.5 | 125 | 143.75 | 256.25 | 165.625 | 309.375 | 446.875 | 409.375 | 0 | 0 | 0 | 0 | 0 | 684.375 | 715.625 | 759.375 | 1168.75 | 643.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5840.625
| Predicted Wages | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 950 | 950 | 900 | 900 | 925 | 925 | 900 | 900 | 950 | 950 | 900 | 900 | 0 | 0 | 0 | 0 | 13050
| External Outgoing Payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| APR Repayment (16.86%) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.4543 | 111.093 | 110.7328 | 110.3737 | 110.0159 | 109.6592 | 109.3036 | 175.8218 | 175.2517 | 174.6835 | 174.1171 | 173.5526 | 0 | 0 | 0 | 0 | 1646.0592
| Office Rent | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 3163.5 | 0 | 0 | 0 | 0 | 24042.6
| Utilities | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 250 | 0 | 0 | 0 | 0 | 1900
| IT Infrastructure | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 500 | 0 | 0 | 0 | 0 | 3800
| External Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
| Cumulative Rent Expenses | 632.7 | 1265.4 | 1898.1 | 2530.8 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 2530.8 | 3163.5 | 3796.2 | 4428.9 | 5061.6 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 2530.8 | 3163.5 | 3796.2 | 4428.9 | 5061.6 | 632.7 | 3796.2 | 0 | 0 | 0 | 0
| Rent Payment Due? | TERM ONE Week 4: TRUE; TERM ONE Week 7: TRUE; TERM ONE Week 10: TRUE; TERM TWO Week 4: TRUE; TERM TWO Week 7: TRUE; TERM TWO Week 10: TRUE; TERM THREE Week 4: TRUE; TERM THREE Week 6: TRUE
| Cumulative Utility Expenses | 50 | 100 | 150 | 200 | 250 | 300 | 50 | 100 | 150 | 200 | 50 | 100 | 150 | 200 | 250 | 300 | 350 | 400 | 450 | 500 | 50 | 100 | 150 | 200 | 50 | 100 | 150 | 200 | 250 | 300 | 350 | 400 | 450 | 700 | 0 | 0 | 0 | 0
| Utility Payment Due? | TERM ONE Week 6: TRUE; TERM ONE Week 10: TRUE; TERM TWO Week 6: TRUE; TERM TWO Week 10: TRUE; TERM THREE Week 6: TRUE
| Cumulative IT Infrastructure Expenses | 100 | 200 | 300 | 400 | 500 | 600 | 100 | 200 | 300 | 400 | 100 | 200 | 300 | 400 | 500 | 600 | 700 | 800 | 900 | 1000 | 100 | 200 | 300 | 400 | 100 | 200 | 300 | 400 | 500 | 600 | 700 | 800 | 900 | 1400 | 0 | 0 | 0 | 0
| IT Infrastructure Payment Due? | TERM ONE Week 6: TRUE; TERM ONE Week 10: TRUE; TERM TWO Week 6: TRUE; TERM TWO Week 10: TRUE; TERM THREE Week 6: TRUE
| Cumulative Contract Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contract Payment Due? | TERM TWO Week 8: TRUE; TERM THREE Week 2: TRUE; TERM THREE Week 3: TRUE
| Total Repayed Loan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.4543 | 222.5473 | 333.28 | 443.6538 | 553.6696 | 663.3288 | 772.6324 | 948.4542 | 1123.706 | 1298.3895 | 1472.5066 | 1646.0592 | 0 | 0 | 0 | 0
| Total Expenditure | 0 | 0 | 12.5 | 2655.8 | 143.75 | 1156.25 | 2063.725 | 309.375 | 446.875 | 2907.475 | 0 | 0 | 0 | 0 | 0 | 684.375 | 715.625 | 5820.975 | 1168.75 | 2143.75 | 2898.1 | 2000 | 1061.4543 | 3559.193 | 1010.7328 | 1010.3737 | 1035.0159 | 1034.6592 | 1009.3036 | 3075.8218 | 2125.2517 | 6186.2835 | 1074.1171 | 6969.7526 | 0 | 0 | 0 | 0 | 54279.2842
Income / £ | bar: TERM ONE Week 1
| External Incoming Payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Financial Backing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34375 | 0 | 0 | 0 | 0 | 0 | 0 | 20625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
| External Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative Contract Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract Revenue Due?
| Total Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34375 | 0 | 0 | 0 | 0 | 0 | 0 | 20625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
Balance / £ | bar: TERM ONE Week 1
| Open | 0 | 0 | 0 | -12.5 | -2668.3 | -2812.05 | -3968.3 | -6032.025 | -6341.4 | -6788.275 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -10380.125 | -11095.75 | -16916.725 | -18085.475 | -20229.225 | -23127.325 | 9247.675 | 8186.2207 | 4627.0277 | 3616.295 | 2605.9212 | 1570.9054 | 536.2462 | 20151.9426 | 17076.1208 | 14950.869 | 8764.5855 | 7690.4684 | 720.7158 | 720.7158 | 720.7158 | 720.7158 | 720.7158
| Total Cashflow | 0 | 0 | -12.5 | -2655.8 | -143.75 | -1156.25 | -2063.725 | -309.375 | -446.875 | -2907.475 | 0 | 0 | 0 | 0 | 0 | -684.375 | -715.625 | -5820.975 | -1168.75 | -2143.75 | -2898.1 | 32375 | -1061.4543 | -3559.193 | -1010.7328 | -1010.3737 | -1035.0159 | -1034.6592 | 19615.6964 | -3075.8218 | -2125.2517 | -6186.2835 | -1074.1171 | -6969.7526 | 0 | 0 | 0 | 0
| Close | 0 | 0 | -12.5 | -2668.3 | -2812.05 | -3968.3 | -6032.025 | -6341.4 | -6788.275 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -10380.125 | -11095.75 | -16916.725 | -18085.475 | -20229.225 | -23127.325 | 9247.675 | 8186.2207 | 4627.0277 | 3616.295 | 2605.9212 | 1570.9054 | 536.2462 | 20151.9426 | 17076.1208 | 14950.869 | 8764.5855 | 7690.4684 | 720.7158 | 720.7158 | 720.7158 | 720.7158 | 720.7158
Iteration Tracking:
Iteration Expenditure Estimates
| Iteration Period | TERM ONE Week 1: User Stories; TERM ONE Week 2: Estimated Total Hrs; TERM ONE Week 3: Cost; TERM ONE Week 4: Cost with Admin Hours (£); TERM ONE Week 5: Per Week Of Iteration (£)
| Iteration 0 (16th Jan - 20th Feb) | TERM ONE Week 1: 001, 002, 004, 020; TERM ONE Week 2: 52; TERM ONE Week 3: 650; TERM ONE Week 4: n/a; TERM ONE Week 5: n/a
| Iteration 1 (20th Feb - 5th Mar) | TERM ONE Week 1: 003, 004, 008, 009, 010, 014, 016; TERM ONE Week 2: 88; TERM ONE Week 3: 1100; TERM ONE Week 4: 2000; TERM ONE Week 5: 1000
| Iteration 2 (5th Mar - 19th Mar) | TERM ONE Week 1: 012, 015, 017, 010, 014; TERM ONE Week 2: 80; TERM ONE Week 3: 1000; TERM ONE Week 4: 1900; TERM ONE Week 5: 950
| Iteration 3 (19th Mar - 2nd Apr) | TERM ONE Week 1: 006, 007, 018, 019; TERM ONE Week 2: 72; TERM ONE Week 3: 900; TERM ONE Week 4: 1800; TERM ONE Week 5: 900
| Iteration 4 (2nd Apr - 16th Apr) | TERM ONE Week 1: 021, 022, 023, 027, 028; TERM ONE Week 2: 76; TERM ONE Week 3: 950; TERM ONE Week 4: 1850; TERM ONE Week 5: 925
| Iteration 5 (16th Apr - 30th Apr) | TERM ONE Week 1: 024, 025, 030; TERM ONE Week 2: 72; TERM ONE Week 3: 900; TERM ONE Week 4: 1800; TERM ONE Week 5: 900
| Iteration 6 (30th Apr - 14th May) | TERM ONE Week 1: 011, 013, 026, 029; TERM ONE Week 2: 80; TERM ONE Week 3: 1000; TERM ONE Week 4: 1900; TERM ONE Week 5: 950
| Iteration 7 (14th May - 28th May) | TERM ONE Week 1: -; TERM ONE Week 2: -; TERM ONE Week 3: 900; TERM ONE Week 4: 1800; TERM ONE Week 5: 900
|  | Total: | 440 | 7400 | 13050
Iteration Actual Expenditure
| Iteration Period | TERM ONE Week 1: User Stories; TERM ONE Week 2: Estimated Total Hrs; TERM ONE Week 3: Actual Hrs; TERM ONE Week 4: Hrs Difference; TERM ONE Week 5: Completion; TERM ONE Week 6: Estimated Cost; TERM ONE Week 7: Current Cost; TERM ONE Week 8: Cost Difference; TERM ONE Week 9: Percentage Expenditure; TERM ONE Week 10: Iteration Cost; CHRISTMAS BREAK Break 1: Iteration Budget; CHRISTMAS BREAK Break 2: Remaining Iteration Budget
| Iteration 0 (16th Jan - 20th Feb) | TERM ONE Week 1: 001, 002, 004, 020; TERM ONE Week 2: 52; TERM ONE Week 3: 62; TERM ONE Week 4: 10; TERM ONE Week 5: 100%; TERM ONE Week 6: 650; TERM ONE Week 7: 775; TERM ONE Week 8: 125; TERM ONE Week 9: 119%; TERM ONE Week 10: 4809.38; CHRISTMAS BREAK Break 1: n/a; CHRISTMAS BREAK Break 2: n/a
| Iteration 1 (20th Feb - 5th Mar) | TERM ONE Week 1: 003, 004, 008, 009, 010, 014, 016; TERM ONE Week 2: 88; TERM ONE Week 3: 21; TERM ONE Week 4: -67; TERM ONE Week 5: 45%; TERM ONE Week 6: 1100; TERM ONE Week 7: 262.5; TERM ONE Week 8: -837.5; TERM ONE Week 9: 24%; TERM ONE Week 10: 806.25; CHRISTMAS BREAK Break 1: 2000; CHRISTMAS BREAK Break 2: 1193.75
| Iteration 2 (5th Mar - 19th Mar) | TERM ONE Week 1: 012, 015, 017; TERM ONE Week 2: 0; TERM ONE Week 3: 0; TERM ONE Week 4: 0; TERM ONE Week 5: 0%; TERM ONE Week 6: 1000; TERM ONE Week 7: £ -; TERM ONE Week 8: -1000; TERM ONE Week 9: 0%; TERM ONE Week 10: £ -; CHRISTMAS BREAK Break 1: 1900; CHRISTMAS BREAK Break 2: 1900
| Iteration 3 (19th Mar - 2nd Apr) | TERM ONE Week 1: 006, 007, 018, 019; TERM ONE Week 2: 0; TERM ONE Week 3: 0; TERM ONE Week 4: 0; TERM ONE Week 5: 0%; TERM ONE Week 6: 900; TERM ONE Week 7: £ -; TERM ONE Week 8: -900; TERM ONE Week 9: 0%; TERM ONE Week 10: £ -; CHRISTMAS BREAK Break 1: 1800; CHRISTMAS BREAK Break 2: 1800
| Iteration 4 (2nd Apr - 16th Apr) | TERM ONE Week 1: 021, 022, 023, 027, 028; TERM ONE Week 2: 0; TERM ONE Week 3: 0; TERM ONE Week 4: 0; TERM ONE Week 5: 0%; TERM ONE Week 6: 950; TERM ONE Week 7: £ -; TERM ONE Week 8: -950; TERM ONE Week 9: 0%; TERM ONE Week 10: £ -; CHRISTMAS BREAK Break 1: 1850; CHRISTMAS BREAK Break 2: 1850
| Iteration 5 (16th Apr - 30th Apr) | TERM ONE Week 1: 024, 025, 030; TERM ONE Week 2: 0; TERM ONE Week 3: 0; TERM ONE Week 4: 0; TERM ONE Week 5: 0%; TERM ONE Week 6: 900; TERM ONE Week 7: £ -; TERM ONE Week 8: -900; TERM ONE Week 9: 0%; TERM ONE Week 10: £ -; CHRISTMAS BREAK Break 1: 1800; CHRISTMAS BREAK Break 2: 1800
| Iteration 6 (30th Apr - 14th May) | TERM ONE Week 1: 011, 013, 026, 029; TERM ONE Week 2: 0; TERM ONE Week 3: 0; TERM ONE Week 4: 0; TERM ONE Week 5: 0%; TERM ONE Week 6: 1000; TERM ONE Week 7: £ -; TERM ONE Week 8: -1000; TERM ONE Week 9: 0%; TERM ONE Week 10: £ -; CHRISTMAS BREAK Break 1: 1900; CHRISTMAS BREAK Break 2: 1900
| Iteration 7 (14th May - 28th May) | TERM ONE Week 1: -; TERM ONE Week 2: 0; TERM ONE Week 3: 0; TERM ONE Week 4: 0; TERM ONE Week 5: 0; TERM ONE Week 6: 900; TERM ONE Week 7: £ -; TERM ONE Week 8: -900; TERM ONE Week 9: 0%; TERM ONE Week 10: £ -; CHRISTMAS BREAK Break 1: 1800; CHRISTMAS BREAK Break 2: 1800
|  | Total: | 140 | 83 | -57 | 18% | 7400 | 1037.5 | -6362.5 | 18% | 5615.63 | 13050 | 12243.75
Iteration 0
| User Story | Estimated Hrs | Actual Hrs | Hrs Difference | Completion | Estimated Cost | Current Cost | Cost Difference | % Expenditure |  |  | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Programming Hrs | Admin Hours Hrs
| 1 | 16 | 38 | 22 | 100% | 200 | 475 | 275 | 238% |  |  | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17
| 2 | 8 | 16 | 8 | 100% | 100 | 200 | 100 | 200% |  | Daniel Bishop | 0 | 5 | 0 | 4 | 0 | 0 | 9 | 15
| 5 | 4 | 2 | -2 | 100% | 50 | 25 | -25 | 50% |  | Oliver Clarke | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.25
| 20 | 24 | 6 | -18 | 100% | 300 | 75 | -225 | 25% |  | James Gardner | 1 | 7 | 12 | 13 | 0 | 0 | 33 | 32.5
[11 empty] | Stijn Marynissen | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.25
[11 empty] | Che McKirgan | 0 | 5 | 6 | 9 | 0 | 0 | 20 | 26
[11 empty] | Cameron Smith | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.75
[11 empty] | Oliver Still | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.25
| Total: | 52 | 62 | 10 | 100% | 650 | 775 | 125 | 119% |  | Eric Walker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.75
[12 empty] | 2020-02-17: Total Hours: | 62 | 322.75
[12 empty] | 2020-02-17: Combined: | 384.75
[12 empty] | 2020-02-17: Current Cost | Budget | Remaining Budget
[12 empty] | 2020-02-17: 4809.38 | n/a | n/a
Iteration 1
| User Story | Estimated Hrs | Actual Hrs | Hrs Difference | Completion | Estimated Cost | Current Cost | Cost Difference | % Expenditure |  |  | Week 7 | Week 8 | Week 9 | Programming Hrs | Admin Hours Hrs
| 3 | 4 | 4 | 0 | 50% | 50 | 50 | £ - | 100% |  |  | 2020-01-13: 2020-02-17; 2020-01-20: 2020-02-24; 2020-01-27: 2020-03-02
| 4 | 4 | 3 | -1 | 50% | 50 | 37.5 | -12.5 | 75% |  | Daniel Bishop | 2020-01-13: 3; 2020-02-03: 3; 2020-02-10: 1
| 8 | 8 | 3 | -5 | 100% | 100 | 37.5 | -62.5 | 38% |  | Oliver Clarke | 2020-01-13: 0; 2020-02-03: 0; 2020-02-10: 26.5
| 9 | 8 | 3 | -5 | 100% | 100 | 37.5 | -62.5 | 38% |  | James Gardner | 2020-01-13: 4; 2020-02-03: 4; 2020-02-10: 1.5
| 10 | 16 | 0 | -16 | 0% | 200 | £ - | -200 | 0% |  | Stijn Marynissen | 2020-01-13: 3; 2020-02-03: 3; 2020-02-10: 1
| 14 | 24 | 2 | -22 | 0% | 300 | 25 | -275 | 8% |  | Che McKirgan | 2020-01-13: 2; 2020-02-03: 2; 2020-02-10: 2
| 16 | 24 | 6 | -18 | 15% | 300 | 75 | -225 | 25% |  | Cameron Smith | 2020-01-13: 3; 2020-02-03: 3; 2020-02-10: 2
[11 empty] | Oliver Still | 2020-01-13: 3; 2020-02-03: 3; 2020-02-10: 8.5
| Total: | 88 | 21 | -67 | 45% | 1100 | 262.5 | -837.5 | 40% |  | Eric Walker | 2020-01-13: 3; 2020-02-03: 3; 2020-02-10: 1
[14 empty] | Total Hours: | 21 | 43.5
[14 empty] | Combined: | 64.5
[14 empty] | Current Cost | Budget | Remaining Budget
[14 empty] | 806.25 | 2000 | 1193.75