## Finance Report II
Finance Report II - 06/03/2020
Project Budget:
|  | Budget | Current Expenditure | Predicted Expenditure | Remaining Budget | Predicted Remaining
Overhead Expenditure
| Office Rent | 24042.6 | 13919.4 | 24042.6 | 10123.2 | 0
| Office Bills and Utilities | 1900 | 1100 | 1900 | 800 | 0
| IT Infrastructure | 3800 | 2200 | 3800 | 1600 | 0
| Contracts | 4000 | 179.6 | 718.4 | 3820.4 | 3282
| Loan Repayments | 1646.0592 | 111.4543 | 1646.0592 | 1534.6049 | 0
Variable Expenditure
| Wages | 18890.625 | 7815.625 | 18865.625 | 11075 | 84.38
| Overhead | 35388.6592 | 17510.4543 | 32107.0592 | 17878.2049 | 3282
| Variable | 19611.3408 | 7815.625 | 18865.625 | 11795.7158 | 745.7158
| Total Injection | 55000 | 25326.0793 | 50972.6842 | 29673.9207 | 4027.3158
| Overhead Recovery Rate (£/hr) | 23.4168 | 11.5867 | 21.2454
PLEASE NOTE ORANGE HOURS HAVE BEEN UPDATED AND WERE INCORRECT IN REPORT I
Project Cashflow:
| CASHFLOW SUPPORTING DOCUMENT | TERM ONE | [9 empty] | CHRISTMAS BREAK |  |  |  | TERM TWO | [9 empty] | EASTER BREAK |  |  |  | TERM THREE | [9 empty] | TOTAL
| (CF 2019/2020) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Break 1 | Break 2 | Break 3 | Break 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Break 1 | Break 2 | Break 3 | Break 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
| Week Commencing | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-08
Salaries / hrs | bar: 2019-09-30
| Daniel Bishop | 0 | 0 | 0 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2.5 | 6 | 2 | 6 | 7.5 | 3 | 8.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.25
| Oliver Clarke | 0 | 0 | 0 | 1 | 1.5 | 1 | 0 | 3.5 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5.5 | 6.25 | 13 | 8 | 29 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86
| James Gardner | 0 | 0 | 1 | 3 | 1.5 | 2.25 | 3.25 | 4 | 9.75 | 6.25 | 0 | 0 | 0 | 0 | 0 | 8.5 | 9.5 | 16.5 | 19 | 5.5 | 12 | 13.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115.25
| Stijn Marynissen | 0 | 0 | 0 | 1 | 1 | 4 | 1 | 3 | 1.75 | 4.75 | 0 | 0 | 0 | 0 | 0 | 9 | 8.5 | 7 | 15 | 4 | 4.5 | 6.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.75
| Che McKirgan | 0 | 0 | 0 | 1 | 1.5 | 3.75 | 1 | 2.25 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 6.5 | 9 | 11.5 | 7 | 3.5 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.5
| Cameron Smith | 0 | 0 | 0 | 1 | 1.5 | 8 | 4.5 | 7.5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 6 | 4.75 | 7 | 12 | 7 | 3.5 | 13.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84
| Oliver Still | 0 | 0 | 0 | 1 | 3 | 1 | 2.5 | 3 | 9.5 | 4.75 | 0 | 0 | 0 | 0 | 0 | 15.5 | 17.25 | 8.5 | 18 | 9.5 | 18.5 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.5
| Eric Walker | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1.5 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 3.25 | 3.5 | 3 | 1 | 3 | 4.5 | 7.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38
Expenses / £ | bar: 2019-09-30
| Wages | £ - | £ - | 12.5 | 125 | 143.75 | 256.25 | 165.63 | 309.38 | 446.88 | 409.38 | £ - | £ - | £ - | £ - | £ - | 684.38 | 768.75 | 740.63 | 1193.75 | 643.75 | 981.25 | 934.38 | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 7815.63
| Predicted Wages | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 1000 | 1000 | 950 | 950 | 900 | 900 | 925 | 925 | 900 | 900 | 950 | 950 | 900 | 900 | £ - | £ - | £ - | £ - | 11050
| Unused Wages | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 18.75 | 65.63 | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 84.38
| External Outgoing Payments | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ -
| APR Repayment (16.86%) | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 111.45 | 111.09 | 110.73 | 110.37 | 110.02 | 109.66 | 109.3 | 175.82 | 175.25 | 174.68 | 174.12 | 173.55 | £ - | £ - | £ - | £ - | 1646.06
| Office Rent | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 3163.5 | £ - | £ - | £ - | £ - | 24042.6
| Utilities | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 250 | £ - | £ - | £ - | £ - | 1900
| IT Infrastructure | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 500 | £ - | £ - | £ - | £ - | 3800
| External Contracts | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 179.6 | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 359.2 | 179.6 | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 718.4
| Cumulative Rent Expenses | 632.7 | 1265.4 | 1898.1 | 2530.8 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 2530.8 | 3163.5 | 3796.2 | 4428.9 | 5061.6 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 2530.8 | 3163.5 | 3796.2 | 4428.9 | 5061.6 | 632.7 | 3796.2 | £ - | £ - | £ - | £ -
| Rent Payment Due? | 2019-10-21: TRUE; 2019-11-11: TRUE; 2019-12-02: TRUE; 2020-01-27: TRUE; 2020-02-17: TRUE; 2020-03-09: TRUE; 2020-05-04: TRUE; 2020-05-18: TRUE
| Cumulative Utility Expenses | 50 | 100 | 150 | 200 | 250 | 300 | 50 | 100 | 150 | 200 | 50 | 100 | 150 | 200 | 250 | 300 | 350 | 400 | 450 | 500 | 50 | 100 | 150 | 200 | 50 | 100 | 150 | 200 | 250 | 300 | 350 | 400 | 450 | 700 | £ - | £ - | £ - | £ -
| Utility Payment Due? | 2019-11-04: TRUE; 2019-12-02: TRUE; 2020-02-10: TRUE; 2020-03-09: TRUE; 2020-05-18: TRUE
| Cumulative IT Infrastructure Expenses | 100 | 200 | 300 | 400 | 500 | 600 | 100 | 200 | 300 | 400 | 100 | 200 | 300 | 400 | 500 | 600 | 700 | 800 | 900 | 1000 | 100 | 200 | 300 | 400 | 100 | 200 | 300 | 400 | 500 | 600 | 700 | 800 | 900 | 1400 | £ - | £ - | £ - | £ -
| IT Infrastructure Payment Due? | 2019-11-04: TRUE; 2019-12-02: TRUE; 2020-02-10: TRUE; 2020-03-09: TRUE; 2020-05-18: TRUE
| Cumulative Contract Expenditure | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 179.6 | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 359.2 | 179.6 | £ - | £ - | £ - | £ - | £ - | £ - | £ -
| Contract Payment Due? | 2020-02-24: TRUE; 2020-04-20: TRUE; 2020-04-27: TRUE
| Total Repayed Loan | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 111.45 | 222.55 | 333.28 | 443.65 | 553.67 | 663.33 | 772.63 | 948.45 | 1123.71 | 1298.39 | 1472.51 | 1646.06 | £ - | £ - | £ - | £ -
| Total Expenditure | £ - | £ - | 12.5 | 2655.8 | 143.75 | 1156.25 | 2063.73 | 309.38 | 446.88 | 2907.48 | £ - | £ - | £ - | £ - | £ - | 684.38 | 768.75 | 5802.23 | 1193.75 | 2143.75 | 2879.35 | 1113.98 | 1061.45 | 3559.19 | 1010.73 | 1010.37 | 1035.02 | 1034.66 | 1009.3 | 1435.02 | 1304.85 | 6186.28 | 1074.12 | 6969.75 | £ - | £ - | £ - | £ - | 50972.68
Income / £ | bar: 2019-09-30
| External Incoming Payments | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ -
| Financial Backing | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 34375 | £ - | £ - | £ - | £ - | £ - | £ - | 20625 | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 55000
| External Contracts | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 251.44 | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 502.88 | 251.44 | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 1005.76
| Cumulative Contract Revenue | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 251.44 | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 502.88 | 251.44 | £ - | £ - | £ - | £ - | £ - | £ - | £ -
| Contract Revenue Due? | 2020-02-24: TRUE; 2020-04-20: TRUE; 2020-04-27: TRUE
| Total Revenue | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 34626.44 | £ - | £ - | £ - | £ - | £ - | £ - | 20625 | 502.88 | 251.44 | £ - | £ - | £ - | £ - | £ - | £ - | £ - | 56005.76
Balance / £ | bar: 2019-09-30
| Open | £ - | £ - | £ - | -12.5 | -2668.3 | -2812.05 | -3968.3 | -6032.03 | -6341.4 | -6788.28 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -10380.13 | -11148.88 | -16951.1 | -18144.85 | -20288.6 | -23167.95 | 10344.52 | 9283.06 | 5723.87 | 4713.13 | 3702.76 | 2667.75 | 1633.09 | 21248.78 | 20316.64 | 19263.23 | 13076.95 | 12002.83 | 5033.08 | 5033.08 | 5033.08 | 5033.08 | 5033.08
| Total Cashflow | £ - | £ - | -12.5 | -2655.8 | -143.75 | -1156.25 | -2063.73 | -309.38 | -446.88 | -2907.48 | £ - | £ - | £ - | £ - | £ - | -684.38 | -768.75 | -5802.23 | -1193.75 | -2143.75 | -2879.35 | 33512.47 | -1061.45 | -3559.19 | -1010.73 | -1010.37 | -1035.02 | -1034.66 | 19615.7 | -932.14 | -1053.41 | -6186.28 | -1074.12 | -6969.75 | £ - | £ - | £ - | £ -
| Close | £ - | £ - | -12.5 | -2668.3 | -2812.05 | -3968.3 | -6032.03 | -6341.4 | -6788.28 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -10380.13 | -11148.88 | -16951.1 | -18144.85 | -20288.6 | -23167.95 | 10344.52 | 9283.06 | 5723.87 | 4713.13 | 3702.76 | 2667.75 | 1633.09 | 21248.78 | 20316.64 | 19263.23 | 13076.95 | 12002.83 | 5033.08 | 5033.08 | 5033.08 | 5033.08 | 5033.08
Iteration Tracking:
Iteration Expenditure Estimates
| Iteration Period | 2019-09-30: User Stories; 2019-10-07: Estimated Total Hrs; 2019-10-14: Cost; 2019-10-21: Cost with Admin Hours (£); 2019-10-28: Per Week Of Iteration (£)
| Iteration 0 (16th Jan - 20th Feb) | 2019-09-30: 001, 002, 004, 020; 2019-10-07: 52; 2019-10-14: 650; 2019-10-21: n/a; 2019-10-28: n/a
| Iteration 1 (20th Feb - 5th Mar) | 2019-09-30: 003, 004, 008, 009, 010, 014, 016; 2019-10-07: 88; 2019-10-14: 1100; 2019-10-21: 2000; 2019-10-28: 1000
| Iteration 2 (5th Mar - 19th Mar) | 2019-09-30: 012, 015, 017, 010, 014; 2019-10-07: 80; 2019-10-14: 1000; 2019-10-21: 1900; 2019-10-28: 950
| Iteration 3 (19th Mar - 2nd Apr) | 2019-09-30: 006, 007, 018, 019; 2019-10-07: 72; 2019-10-14: 900; 2019-10-21: 1800; 2019-10-28: 900
| Iteration 4 (2nd Apr - 16th Apr) | 2019-09-30: 021, 022, 023, 027, 028; 2019-10-07: 76; 2019-10-14: 950; 2019-10-21: 1850; 2019-10-28: 925
| Iteration 5 (16th Apr - 30th Apr) | 2019-09-30: 024, 025, 030; 2019-10-07: 72; 2019-10-14: 900; 2019-10-21: 1800; 2019-10-28: 900
| Iteration 6 (30th Apr - 14th May) | 2019-09-30: 011, 013, 026, 029; 2019-10-07: 80; 2019-10-14: 1000; 2019-10-21: 1900; 2019-10-28: 950
| Iteration 7 (14th May - 28th May) | 2019-09-30: -; 2019-10-07: -; 2019-10-14: 900; 2019-10-21: 1800; 2019-10-28: 900
|  | Total: | 440 | 7400 | 13050
Iteration Actual Expenditure
| Iteration Period | 2019-09-30: User Stories; 2019-10-07: Estimated Total Hrs; 2019-10-14: Actual Hrs; 2019-10-21: Hrs Difference; 2019-10-28: Completion; 2019-11-04: Estimated Cost; 2019-11-11: Current Cost; 2019-11-18: Cost Difference; 2019-11-25: Percentage Expenditure; 2019-12-02: Iteration Cost; 2019-12-09: Iteration Budget; 2019-12-16: Remaining Iteration Budget; 2019-12-23: Notes
| Iteration 0 (16th Jan - 20th Feb) | 2019-09-30: 001, 002, 004, 020; 2019-10-07: 52; 2019-10-14: 62; 2019-10-21: 10; 2019-10-28: 100%; 2019-11-04: 650; 2019-11-11: 775; 2019-11-18: 125; 2019-11-25: 119%; 2019-12-02: 4809.38; 2019-12-09: n/a; 2019-12-16: n/a; 2019-12-23: Iteration 0 is seen as a research & development stage. Was started before any budget had been made, hence no budget. Significantly underestimated programming time on GUI development.
| Iteration 1 (20th Feb - 5th Mar) | 2019-09-30: 003, 004, 008, 009, 010, 014, 016; 2019-10-07: 88; 2019-10-14: 66.25; 2019-10-21: -21.75; 2019-10-28: 91%; 2019-11-04: 1100; 2019-11-11: 828.13; 2019-11-18: -271.88; 2019-11-25: 75%; 2019-12-02: 1696.88; 2019-12-09: 2000; 2019-12-16: 303.13; 2019-12-23: Well within budget, however user stories have not been fully complete and are now passed into the next iteration. Completion to expenditure percentage ratio is good. Will have to be careful that user stories do not start to pile up between iterations.
| Iteration 2 (5th Mar - 19th Mar) | 2019-09-30: 012, 015, 017, 010, 014; 2019-10-07: 80; 2019-10-14: 0; 2019-10-21: -80; 2019-10-28: 0%; 2019-11-04: 1000; 2019-11-11: £ -; 2019-11-18: -1000; 2019-11-25: 0%; 2019-12-02: £ -; 2019-12-09: 1900; 2019-12-16: 1900
| Iteration 3 (19th Mar - 2nd Apr) | 2019-09-30: 006, 007, 018, 019; 2019-10-07: 72; 2019-10-14: 0; 2019-10-21: -72; 2019-10-28: 0%; 2019-11-04: 900; 2019-11-11: £ -; 2019-11-18: -900; 2019-11-25: 0%; 2019-12-02: £ -; 2019-12-09: 1800; 2019-12-16: 1800
| Iteration 4 (2nd Apr - 16th Apr) | 2019-09-30: 021, 022, 023, 027, 028; 2019-10-07: 76; 2019-10-14: 0; 2019-10-21: -76; 2019-10-28: 0%; 2019-11-04: 950; 2019-11-11: £ -; 2019-11-18: -950; 2019-11-25: 0%; 2019-12-02: £ -; 2019-12-09: 1850; 2019-12-16: 1850
| Iteration 5 (16th Apr - 30th Apr) | 2019-09-30: 024, 025, 030; 2019-10-07: 72; 2019-10-14: 0; 2019-10-21: -72; 2019-10-28: 0%; 2019-11-04: 900; 2019-11-11: £ -; 2019-11-18: -900; 2019-11-25: 0%; 2019-12-02: £ -; 2019-12-09: 1800; 2019-12-16: 1800
| Iteration 6 (30th Apr - 14th May) | 2019-09-30: 011, 013, 026, 029; 2019-10-07: 80; 2019-10-14: 0; 2019-10-21: -80; 2019-10-28: 0%; 2019-11-04: 1000; 2019-11-11: £ -; 2019-11-18: -1000; 2019-11-25: 0%; 2019-12-02: £ -; 2019-12-09: 1900; 2019-12-16: 1900
| Iteration 7 (14th May - 28th May) | 2019-09-30: -; 2019-10-07: 0; 2019-10-14: 0; 2019-10-21: 0; 2019-10-28: 0%; 2019-11-04: 900; 2019-11-11: £ -; 2019-11-18: -900; 2019-11-25: 0%; 2019-12-02: £ -; 2019-12-09: 1800; 2019-12-16: 1800
|  | Total: | 520 | 128.25 | -391.75 | 24% | 7400 | 1603.13 | -5796.88 | 24% | 6506.25 | 13050 | 11353.13
Iteration 0
| User Story | 2019-09-30: Estimated Hrs; 2019-10-07: Actual Hrs; 2019-10-14: Hrs Difference; 2019-10-21: Completion; 2019-10-28: Estimated Cost; 2019-11-04: Current Cost; 2019-11-11: Cost Difference; 2019-11-18: Percentage Expenditure; 2019-12-09: Week 2; 2019-12-16: Week 3; 2019-12-23: Week 4; 2019-12-30: Week 5; 2020-01-06: Week 6; 2020-01-13: Week 7; 2020-01-20: Programming Hrs; 2020-01-27: Admin Hours Hrs
| 1 | 2019-09-30: 16; 2019-10-07: 38; 2019-10-14: 22; 2019-10-21: 100%; 2019-10-28: 200; 2019-11-04: 475; 2019-11-11: 275; 2019-11-18: 238%; 2019-12-09: 2020-01-13; 2019-12-16: 2020-01-20; 2019-12-23: 2020-01-27; 2019-12-30: 2020-02-03; 2020-01-06: 2020-02-10; 2020-01-13: 2020-02-17
| 2 | 2019-09-30: 8; 2019-10-07: 16; 2019-10-14: 8; 2019-10-21: 100%; 2019-10-28: 100; 2019-11-04: 200; 2019-11-11: 100; 2019-11-18: 200%; 2019-12-02: Daniel Bishop; 2019-12-09: 0; 2019-12-16: 5; 2019-12-23: 0; 2019-12-30: 4; 2020-01-06: 0; 2020-01-13: 0; 2020-01-20: 9; 2020-01-27: 15
| 5 | 2019-09-30: 4; 2019-10-07: 2; 2019-10-14: -2; 2019-10-21: 100%; 2019-10-28: 50; 2019-11-04: 25; 2019-11-11: -25; 2019-11-18: 50%; 2019-12-02: Oliver Clarke; 2019-12-09: 0; 2019-12-16: 0; 2019-12-23: 0; 2019-12-30: 0; 2020-01-06: 0; 2020-01-13: 0; 2020-01-20: 0; 2020-01-27: 75.25
| 20 | 2019-09-30: 24; 2019-10-07: 6; 2019-10-14: -18; 2019-10-21: 100%; 2019-10-28: 300; 2019-11-04: 75; 2019-11-11: -225; 2019-11-18: 25%; 2019-12-02: James Gardner; 2019-12-09: 1; 2019-12-16: 7; 2019-12-23: 12; 2019-12-30: 13; 2020-01-06: 0; 2020-01-13: 0; 2020-01-20: 33; 2020-01-27: 32.5
[11 empty] | Stijn Marynissen | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.25
[11 empty] | Che McKirgan | 0 | 5 | 6 | 9 | 0 | 0 | 20 | 26
[11 empty] | Cameron Smith | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.75
[11 empty] | Oliver Still | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.25
| Total: | 2019-09-30: 52; 2019-10-07: 62; 2019-10-14: 10; 2019-10-21: 100%; 2019-10-28: 650; 2019-11-04: 775; 2019-11-11: 125; 2019-11-18: 119%; 2019-12-02: Eric Walker; 2019-12-09: 0; 2019-12-16: 0; 2019-12-23: 0; 2019-12-30: 0; 2020-01-06: 0; 2020-01-13: 0; 2020-01-20: 0; 2020-01-27: 14.75
[17 empty] | Total Hours: | 62 | 322.75
[17 empty] | Combined: | 384.75
[17 empty] | Current Cost | Budget | Remaining Budget
[17 empty] | 4809.38 | n/a | n/a
Iteration 1
| User Story | 2019-09-30: Estimated Hrs; 2019-10-07: Actual Hrs; 2019-10-14: Hrs Difference; 2019-10-21: Completion; 2019-10-28: Estimated Cost; 2019-11-04: Current Cost; 2019-11-11: Cost Difference; 2019-11-18: Percentage Expenditure; 2019-12-09: Week 7; 2019-12-16: Week 8; 2019-12-23: Week 9; 2019-12-30: Programming Hrs; 2020-01-06: Total Admin Hrs
| 3 | 2019-09-30: 4; 2019-10-07: 15; 2019-10-14: 11; 2019-10-21: 100%; 2019-10-28: 50; 2019-11-04: 187.5; 2019-11-11: 137.5; 2019-11-18: 375%; 2019-12-09: 2020-02-17; 2019-12-16: 2020-02-24; 2019-12-23: 2020-03-02
| 4 | 2019-09-30: 4; 2019-10-07: 8.25; 2019-10-14: 4.25; 2019-10-21: 100%; 2019-10-28: 50; 2019-11-04: 103.125; 2019-11-11: 53.125; 2019-11-18: 206.2%; 2019-12-02: Daniel Bishop; 2019-12-09: 3; 2019-12-16: 5.25; 2019-12-23: 0; 2019-12-30: 8.25; 2020-01-06: 2
| 8 | 2019-09-30: 8; 2019-10-07: 1.5; 2019-10-14: -6.5; 2019-10-21: 100%; 2019-10-28: 100; 2019-11-04: 18.75; 2019-11-11: -81.25; 2019-11-18: 19%; 2019-12-02: Oliver Clarke; 2019-12-09: 0; 2019-12-16: 3; 2019-12-23: 0; 2019-12-30: 3; 2020-01-06: 26
| 9 | 2019-09-30: 8; 2019-10-07: 2; 2019-10-14: -6; 2019-10-21: 100%; 2019-10-28: 100; 2019-11-04: 25; 2019-11-11: -75; 2019-11-18: 25%; 2019-12-02: James Gardner; 2019-12-09: 3; 2019-12-16: 10; 2019-12-23: 1; 2019-12-30: 14; 2020-01-06: 6.75
| 10 | 2019-09-30: 16; 2019-10-07: 13; 2019-10-14: -3; 2019-10-21: 67%; 2019-10-28: 200; 2019-11-04: 162.5; 2019-11-11: -37.5; 2019-11-18: 81%; 2019-12-02: Stijn Marynissen; 2019-12-09: 3; 2019-12-16: 4.25; 2019-12-23: 2; 2019-12-30: 9.25; 2020-01-06: 4
| 14 | 2019-09-30: 24; 2019-10-07: 10.5; 2019-10-14: -13.5; 2019-10-21: 70%; 2019-10-28: 300; 2019-11-04: 131.25; 2019-11-11: -168.75; 2019-11-18: 44%; 2019-12-02: Che McKirgan; 2019-12-09: 0; 2019-12-16: 4.5; 2019-12-23: 3; 2019-12-30: 7.5; 2020-01-06: 2
| 16 | 2019-09-30: 24; 2019-10-07: 18; 2019-10-14: -6; 2019-10-21: 100%; 2019-10-28: 300; 2019-11-04: 225; 2019-11-11: -75; 2019-11-18: 75%; 2019-12-02: Cameron Smith; 2019-12-09: 3; 2019-12-16: 2.25; 2019-12-23: 2.5; 2019-12-30: 7.75; 2020-01-06: 12
[11 empty] | Oliver Still | 3 | 4.75 | 2.5 | 10.25 | 15.75
| Total: | 2019-09-30: 88; 2019-10-07: 68.25; 2019-10-14: -19.75; 2019-10-21: 91%; 2019-10-28: 1100; 2019-11-04: 853.125; 2019-11-11: -246.875; 2019-11-18: 77.56%; 2019-12-02: Eric Walker; 2019-12-09: 3; 2019-12-16: 5.25; 2019-12-23: 0; 2019-12-30: 8.25; 2020-01-06: 3
[14 empty] | Total Hours: | 68.25 | 71.5
[14 empty] | Combined: | 139.75
[14 empty] | Current Cost | Budget | Remaining Budget
[14 empty] | 1746.88 | 2000 | 253.13
Iteration 2
| User Story | 2019-09-30: Estimated Hrs; 2019-10-07: Actual Hrs; 2019-10-14: Hrs Difference; 2019-10-21: Completion; 2019-10-28: Estimated Cost; 2019-11-04: Current Cost; 2019-11-11: Cost Difference; 2019-11-18: Percentage Expenditure; 2019-12-09: Week 9; 2019-12-16: Week 10; 2019-12-23: Break 1; 2019-12-30: Programming Hrs; 2020-01-06: Total Admin Hrs
| 12 | 2019-09-30: 8; 2019-10-14: -8; 2019-10-21: 0%; 2019-10-28: 100; 2019-11-04: £ -; 2019-11-11: -100; 2019-11-18: 0%; 2019-12-09: 2020-02-17; 2019-12-16: 2020-02-24; 2019-12-23: 2020-03-02
| 15 | 2019-09-30: 16; 2019-10-14: -16; 2019-10-21: 0%; 2019-10-28: 200; 2019-11-04: £ -; 2019-11-11: -200; 2019-11-18: 0%; 2019-12-02: Daniel Bishop; 2019-12-30: 0
| 17 | 2019-09-30: 56; 2019-10-14: -56; 2019-10-21: 0%; 2019-10-28: 700; 2019-11-04: £ -; 2019-11-11: -700; 2019-11-18: 0%; 2019-12-02: Oliver Clarke; 2019-12-30: 0
| 10 (Overdue) | 2019-09-30: 3; 2019-10-14: -3; 2019-10-21: 67%; 2019-10-28: 37.5; 2019-11-04: £ -; 2019-11-11: -37.5; 2019-11-18: 0%; 2019-12-02: James Gardner; 2019-12-30: 0
| 14 (Overdue) | 2019-09-30: 13.5; 2019-10-14: -13.5; 2019-10-21: 70%; 2019-10-28: 168.75; 2019-11-04: £ -; 2019-11-11: -168.75; 2019-11-18: 0%; 2019-12-02: Stijn Marynissen; 2019-12-30: 0
[11 empty] | Che McKirgan |  |  |  | 0
[11 empty] | Cameron Smith |  |  |  | 0
[11 empty] | Oliver Still |  |  |  | 0
| Total: | 2019-09-30: 96.5; 2019-10-07: 0; 2019-10-14: -96.5; 2019-10-21: 0%; 2019-10-28: 1206.25; 2019-11-04: £ -; 2019-11-11: -1206.25; 2019-11-18: 0%; 2019-12-02: Eric Walker; 2019-12-30: 0
[14 empty] | Total Hours: | 0 | 0
[14 empty] | Combined: | 0
[14 empty] | Current Cost | Budget | Remaining Budget
[14 empty] | £ - | 1900 | 1900