## Finance Report III
Finance Report III - 30/04/2020
Project Budget:
|  | Budget | Current Expenditure | Predicted Expenditure | Remaining Budget | Predicted Remaining
Overhead Expenditure
| Office Rent | 24042.6 | 13919.4 | 24042.6 | 10123.2 | 0
| Office Bills and Utilities | 1900 | 1100 | 1900 | 800 | 0
| IT Infrastructure | 3800 | 2200 | 3800 | 1600 | 0
| Contracts | 4000 | 718.4 | 718.4 | 3281.6 | 3282
| Loan Repayments | 1646.0592 | 1123.706 | 1646.0592 | 522.3533 | 0
Variable Expenditure
| Wages | 18890.625 | 15328.125 | 19028.125 | 3562.5
| Overhead | 35388.6592 | 19061.506 | 32107.0592 | 16327.1533 | 3282
| Variable | 19611.3408 | 15328.125 | 19028.125 | 4283.2158 | 583.2158 | WAGES ARE PREDICTED TO OVERSPEND, THIS HAS BEEN NOTED AND IS NOT AN ISSUE. THIS IS BECAUSE WAGES HAD A BUFFER IN THE CASE OF OVERSPENDING AND THE BUDEGT CAN BE EXPANDED IF NEEDED FROM THE SURPLUS CONTRACTS BUDGET.
| Total Injection | 55000 | 34389.631 | 51135.1842 | 20610.369 | 3864.8158
| Overhead Recovery Rate (£/hr) | 23.4168 | 12.6131 | 21.2454
PLEASE NOTE ORANGE HOURS HAVE BEEN UPDATED AND WERE INCORRECT IN REPORT I
HOURS MARKED ORANGE AS REPORT WAS SUBMITTED MID-WEEK, HENCE ONLY PROVISIONAL
Project Cashflow:
| CASHFLOW SUPPORTING DOCUMENT | TERM ONE | [9 empty] | CHRISTMAS BREAK |  |  |  | TERM TWO | [9 empty] | EASTER BREAK |  |  |  | TERM THREE | [9 empty] | TOTAL
| (CF 2019/2020) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Break 1 | Break 2 | Break 3 | Break 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Break 1 | Break 2 | Break 3 | Break 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
| Week Commencing | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-08
Salaries / hrs | bar: 2019-09-30
| Daniel Bishop | 0 | 0 | 0 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2.5 | 6 | 2 | 6 | 7.5 | 3 | 8.25 | 7 | 1.75 | 0 | 8.25 | 10.5 | 18.25 | 8.5 | 10 | 6.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110.75
| Oliver Clarke | 0 | 0 | 0 | 1 | 1.5 | 1 | 0 | 3.5 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5.5 | 6.25 | 13 | 8 | 29 | 7.5 | 9 | 5 | 6 | 8.25 | 9.25 | 5.75 | 18.5 | 18.5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.25
| James Gardner | 0 | 0 | 1 | 3 | 1.5 | 2.25 | 3.25 | 4 | 9.75 | 6.25 | 0 | 0 | 0 | 0 | 0 | 8.5 | 9.5 | 16.5 | 19 | 5.5 | 12 | 13.25 | 9 | 8.5 | 6.75 | 11.25 | 26.25 | 14.75 | 5.25 | 19 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218.25
| Stijn Marynissen | 0 | 0 | 0 | 1 | 1 | 4 | 1 | 3 | 1.75 | 4.75 | 0 | 0 | 0 | 0 | 0 | 9 | 8.5 | 7 | 15 | 4 | 4.5 | 6.25 | 4 | 4.5 | 5 | 6.25 | 8.25 | 5.75 | 6.5 | 10.5 | 2.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.25
| Che McKirgan | 0 | 0 | 0 | 1 | 1.5 | 3.75 | 1 | 2.25 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 6.5 | 9 | 11.5 | 7 | 3.5 | 9.5 | 8 | 8 | 1 | 1 | 7 | 10.5 | 12.25 | 1.25 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.25
| Cameron Smith | 0 | 0 | 0 | 1 | 1.5 | 8 | 4.5 | 7.5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 6 | 4.75 | 7 | 12 | 7 | 3.5 | 13.25 | 12.5 | 15.25 | 12 | 11.5 | 6.5 | 9 | 2.25 | 16.5 | 20.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.75
| Oliver Still | 0 | 0 | 0 | 1 | 3 | 1 | 2.5 | 3 | 9.5 | 4.75 | 0 | 0 | 0 | 0 | 0 | 15.5 | 17.25 | 8.5 | 18 | 9.5 | 18.5 | 9.5 | 10.5 | 12.25 | 1.5 | 6.75 | 7.5 | 18.5 | 17 | 23.75 | 13.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232.5
| Eric Walker | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1.5 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 3.25 | 3.5 | 3 | 1 | 3 | 4.5 | 7.25 | 7.5 | 3.5 | 0.25 | 12 | 12.25 | 14.75 | 7 | 15.5 | 6.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117
Expenses / £ | bar: 2019-09-30
| Wages | 0 | 0 | 12.5 | 125 | 143.75 | 256.25 | 165.625 | 309.375 | 446.875 | 409.375 | 0 | 0 | 0 | 0 | 0 | 684.375 | 768.75 | 740.625 | 1193.75 | 643.75 | 981.25 | 934.375 | 843.75 | 734.375 | 406.25 | 815.625 | 1093.75 | 1215.625 | 965.625 | 1437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15328.125
| Predicted Wages | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 950 | 950 | 900 | 900 | 925 | 925 | 900 | 900 | 950 | 950 | 900 | 900 | 0 | 0 | 0 | 0 | 3700
| Unused Wages | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.75 | 65.625 | 106.25 | 215.625 | 493.75 | 84.375 | -168.75 | -290.625 | -65.625 | -537.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78.125
| External Outgoing Payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| APR Repayment (16.86%) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.4543 | 111.093 | 110.7328 | 110.3737 | 110.0159 | 109.6592 | 109.3036 | 175.8218 | 175.2517 | 174.6835 | 174.1171 | 173.5526 | 0 | 0 | 0 | 0 | 1646.0592
| Office Rent | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 632.7 | 3163.5 | 0 | 0 | 0 | 0 | 24042.6
| Utilities | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 250 | 0 | 0 | 0 | 0 | 1900
| IT Infrastructure | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 500 | 0 | 0 | 0 | 0 | 3800
| External Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359.2 | 179.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 718.4
| Cumulative Rent Expenses | 632.7 | 1265.4 | 1898.1 | 2530.8 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 2530.8 | 3163.5 | 3796.2 | 4428.9 | 5061.6 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 632.7 | 1265.4 | 1898.1 | 2530.8 | 3163.5 | 3796.2 | 4428.9 | 5061.6 | 632.7 | 3796.2 | 0 | 0 | 0 | 0
| Rent Payment Due? | 2019-10-21: TRUE; 2019-11-11: TRUE; 2019-12-02: TRUE; 2020-01-27: TRUE; 2020-02-17: TRUE; 2020-03-09: TRUE; 2020-05-04: TRUE; 2020-05-18: TRUE
| Cumulative Utility Expenses | 50 | 100 | 150 | 200 | 250 | 300 | 50 | 100 | 150 | 200 | 50 | 100 | 150 | 200 | 250 | 300 | 350 | 400 | 450 | 500 | 50 | 100 | 150 | 200 | 50 | 100 | 150 | 200 | 250 | 300 | 350 | 400 | 450 | 700 | 0 | 0 | 0 | 0
| Utility Payment Due? | 2019-11-04: TRUE; 2019-12-02: TRUE; 2020-02-10: TRUE; 2020-03-09: TRUE; 2020-05-18: TRUE
| Cumulative IT Infrastructure Expenses | 100 | 200 | 300 | 400 | 500 | 600 | 100 | 200 | 300 | 400 | 100 | 200 | 300 | 400 | 500 | 600 | 700 | 800 | 900 | 1000 | 100 | 200 | 300 | 400 | 100 | 200 | 300 | 400 | 500 | 600 | 700 | 800 | 900 | 1400 | 0 | 0 | 0 | 0
| IT Infrastructure Payment Due? | 2019-11-04: TRUE; 2019-12-02: TRUE; 2020-02-10: TRUE; 2020-03-09: TRUE; 2020-05-18: TRUE
| Cumulative Contract Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359.2 | 179.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contract Payment Due? | 2020-02-24: TRUE; 2020-04-20: TRUE; 2020-04-27: TRUE
| Total Repayed Loan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.4543 | 222.5473 | 333.28 | 443.6538 | 553.6696 | 663.3288 | 772.6324 | 948.4542 | 1123.706 | 1298.3895 | 1472.5066 | 1646.0592 | 0 | 0 | 0 | 0
| Total Expenditure | 0 | 0 | 12.5 | 2655.8 | 143.75 | 1156.25 | 2063.725 | 309.375 | 446.875 | 2907.475 | 0 | 0 | 0 | 0 | 0 | 684.375 | 768.75 | 5802.225 | 1193.75 | 2143.75 | 2879.35 | 1113.975 | 955.2043 | 3343.568 | 516.9828 | 925.9987 | 1203.7659 | 1325.2842 | 1074.9286 | 1972.5218 | 1304.8517 | 6186.2835 | 1074.1171 | 6969.7526 | 0 | 0 | 0 | 0 | 51135.1842
Income / £ | bar: 2019-09-30
| External Incoming Payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Financial Backing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34375 | 0 | 0 | 0 | 0 | 0 | 0 | 20625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
| External Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502.88 | 251.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005.76
| Cumulative Contract Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502.88 | 251.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contract Revenue Due? | 2020-02-24: TRUE; 2020-04-20: TRUE; 2020-04-27: TRUE
| Total Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34626.44 | 0 | 0 | 0 | 0 | 0 | 0 | 20625 | 502.88 | 251.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56005.76
Balance / £ | bar: 2019-09-30
| Open | 0 | 0 | 0 | -12.5 | -2668.3 | -2812.05 | -3968.3 | -6032.025 | -6341.4 | -6788.275 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -10380.125 | -11148.875 | -16951.1 | -18144.85 | -20288.6 | -23167.95 | 10344.515 | 9389.3107 | 6045.7427 | 5528.76 | 4602.7612 | 3398.9954 | 2073.7112 | 21623.7826 | 20154.1408 | 19100.729 | 12914.4455 | 11840.3284 | 4870.5758 | 4870.5758 | 4870.5758 | 4870.5758 | 4870.5758
| Total Cashflow | 0 | 0 | -12.5 | -2655.8 | -143.75 | -1156.25 | -2063.725 | -309.375 | -446.875 | -2907.475 | 0 | 0 | 0 | 0 | 0 | -684.375 | -768.75 | -5802.225 | -1193.75 | -2143.75 | -2879.35 | 33512.465 | -955.2043 | -3343.568 | -516.9828 | -925.9987 | -1203.7659 | -1325.2842 | 19550.0714 | -1469.6418 | -1053.4117 | -6186.2835 | -1074.1171 | -6969.7526 | 0 | 0 | 0 | 0
| Close | 0 | 0 | -12.5 | -2668.3 | -2812.05 | -3968.3 | -6032.025 | -6341.4 | -6788.275 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -9695.75 | -10380.125 | -11148.875 | -16951.1 | -18144.85 | -20288.6 | -23167.95 | 10344.515 | 9389.3107 | 6045.7427 | 5528.76 | 4602.7612 | 3398.9954 | 2073.7112 | 21623.7826 | 20154.1408 | 19100.729 | 12914.4455 | 11840.3284 | 4870.5758 | 4870.5758 | 4870.5758 | 4870.5758 | 4870.5758
Iteration Tracking:
Iteration Expenditure Estimates
| Iteration Period | 2019-09-30: User Stories; 2019-10-07: Estimated Total Hrs; 2019-10-14: Cost; 2019-10-21: Cost with Admin Hours (£); 2019-10-28: Per Week Of Iteration (£)
| Iteration 0 (16th Jan - 20th Feb) | 2019-09-30: 001, 002, 004, 020; 2019-10-07: 52; 2019-10-14: 650; 2019-10-21: n/a; 2019-10-28: n/a
| Iteration 1 (20th Feb - 5th Mar) | 2019-09-30: 003, 004, 008, 009, 010, 014, 016; 2019-10-07: 88; 2019-10-14: 1100; 2019-10-21: 2000; 2019-10-28: 1000
| Iteration 2 (5th Mar - 19th Mar) | 2019-09-30: 012, 015, 017; 2019-10-07: 80; 2019-10-14: 1000; 2019-10-21: 1900; 2019-10-28: 950
| Iteration 3 (19th Mar - 2nd Apr) | 2019-09-30: 006, 007, 018, 019; 2019-10-07: 72; 2019-10-14: 900; 2019-10-21: 1800; 2019-10-28: 900
| Iteration 4 (2nd Apr - 16th Apr) | 2019-09-30: 021, 022, 023, 027, 028; 2019-10-07: 76; 2019-10-14: 950; 2019-10-21: 1850; 2019-10-28: 925
| Iteration 5 (16th Apr - 30th Apr) | 2019-09-30: 024, 025, 030; 2019-10-07: 72; 2019-10-14: 900; 2019-10-21: 1800; 2019-10-28: 900
| Iteration 6 (30th Apr - 14th May) | 2019-09-30: 011, 013, 026, 029; 2019-10-07: 80; 2019-10-14: 1000; 2019-10-21: 1900; 2019-10-28: 950
| Iteration 7 (14th May - 28th May) | 2019-09-30: -; 2019-10-07: -; 2019-10-14: 900; 2019-10-21: 1800; 2019-10-28: 900
|  | Total: | 440 | 7400 | 13050
Iteration Actual Expenditure
| Iteration Period | 2019-09-30: User Stories; 2019-10-07: Estimated Total Hrs; 2019-10-14: Extra Hours; 2019-10-21: Actual Hrs; 2019-10-28: Hrs Difference; 2019-11-04: Completion; 2019-11-11: Estimated Cost; 2019-11-18: Current Cost; 2019-11-25: Cost Difference; 2019-12-02: Percentage Expenditure; 2019-12-09: Iteration Cost; 2019-12-16: Iteration Budget; 2019-12-23: Remaining Iteration Budget; 2019-12-30: Notes
| Iteration 0 (16th Jan - 20th Feb) | 2019-09-30: 001, 002, 004, 020; 2019-10-07: 52; 2019-10-14: 0; 2019-10-21: 62; 2019-10-28: 10; 2019-11-04: 100%; 2019-11-11: 650; 2019-11-18: 775; 2019-11-25: 125; 2019-12-02: 119%; 2019-12-09: 4809.38; 2019-12-16: n/a; 2019-12-30: Iteration 0 is seen as a research & development stage. Was started before any budget had been made, hence no budget. Under-estimated programming time.
| Iteration 1 (20th Feb - 5th Mar) | 2019-09-30: 003, 004, 008, 009, 010, 014, 016; 2019-10-07: 88; 2019-10-14: 0; 2019-10-21: 68.25; 2019-10-28: -19.75; 2019-11-04: 91%; 2019-11-11: 1100; 2019-11-18: 853.13; 2019-11-25: -246.88; 2019-12-02: 78%; 2019-12-09: 1790.63; 2019-12-16: 2000; 2019-12-23: 209.38; 2019-12-30: Well within budget, however user stories have not been fully complete and are now passed into the next iteration. Completion - expenditure percentage ratio is good. Will have to be careful that user stories do not start to pile up between iterations.
| Iteration 2 (5th Mar - 19th Mar) | 2019-09-30: 012, 015, 017, 010, 014, 029, 031; 2019-10-07: 80; 2019-10-14: 52.5; 2019-10-21: 37.25; 2019-10-28: -95.25; 2019-11-04: 28%; 2019-11-11: 1000; 2019-11-18: 465.63; 2019-11-25: -534.38; 2019-12-02: 47%; 2019-12-09: 1487.5; 2019-12-16: 1900; 2019-12-23: 412.5; 2019-12-30: Included 2 new user stories (31 & 32) to for additional GUI elements, covered by the remaining budget from Iteration 1. Due to external deadlines (VHDL), compeltion is expected to be slightly under again.
| Iteration 3 (19th Mar - 2nd Apr) | 2019-09-30: 006, 007, 018, 019, 010, 012, 015, 017, 029, 032; 2019-10-07: 72; 2019-10-14: 102.5; 2019-10-21: 83.25; 2019-10-28: -91.25; 2019-11-04: 84%; 2019-11-11: 900; 2019-11-18: 1040.63; 2019-11-25: 140.63; 2019-12-02: 116%; 2019-12-09: 1686.88; 2019-12-16: 1800; 2019-12-23: 113.13; 2019-12-30: University course deadlines meant user stories were not complete. User stories increased from 4 to 10 and we completed 7 of them. This meant some followed through to iteration 4.
| Iteration 4 (2nd Apr - 16th Apr) | 2019-09-30: 021, 022, 023, 027, 028, 017, 029, 032; 2019-10-07: 76; 2019-10-14: 61.5; 2019-10-21: 118; 2019-10-28: -19.5; 2019-11-04: 76%; 2019-11-11: 950; 2019-11-18: 1475; 2019-11-25: 525; 2019-12-02: 155%; 2019-12-09: 2188.75; 2019-12-16: 1850; 2019-12-23: -338.75; 2019-12-30: Modules that utilised server handlers needed a second listener thread on the client side in order to effectively function. Thus, one was made half way in between the iteration and development on server modules were delayed.
| Iteration 5 (16th Apr - 30th Apr) | 2019-09-30: 024, 025, 030, 023, 027, 029, 032, 004, 003; 2019-10-07: 72; 2019-10-14: 14.75; 2019-10-21: 86.75; 2019-10-28: 0; 2019-11-04: 60%; 2019-11-11: 900; 2019-11-18: 1084.38; 2019-11-25: 184.38; 2019-12-02: 120%; 2019-12-09: 2140.63; 2019-12-16: 1800; 2019-12-23: -340.63; 2019-12-30: Big push to finish all overdue user stories and begin large merge for next iteration to produce full-featured program. Actual planned user stories mostly complete, apart from webcam which had no progress. O.S. made major updates to previous user stories 003 and 004.
| Iteration 6 (30th Apr - 14th May) | 2019-09-30: 011, 013, 026, 029; 2019-10-07: 80; 2019-10-21: 0; 2019-10-28: -80; 2019-11-04: 100%; 2019-11-11: 1000; 2019-11-18: £ -; 2019-11-25: -1000; 2019-12-02: 0%; 2019-12-09: £ -; 2019-12-16: 1900; 2019-12-23: 1900; 2019-12-30: All assigned user stories were completed as part of the functionality implemented in the previous iterations, leaving the only work to be updates or overdue stories. Story 13 was also outsourced.
| Iteration 7 (14th May - 28th May) | 2019-09-30: -; 2019-10-07: 0; 2019-10-21: 0; 2019-10-28: 0; 2019-11-04: 0%; 2019-11-11: 900; 2019-11-18: £ -; 2019-11-25: -900; 2019-12-02: 0%; 2019-12-09: £ -; 2019-12-16: 1800; 2019-12-23: 1800
|  | Total: | 628 |  | 455.5 | -295.75 | 67% | 7400 | 5693.75 | -1706.25 | 79% | 14103.75 | 13050 | 3755.63
Iteration 0
[12 empty] | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Programming Hrs | Admin Hours Hrs
| User Story | 2019-09-30: Estimated Hrs; 2019-10-07: Actual Hrs; 2019-10-14: Hrs Difference; 2019-10-21: Completion; 2019-10-28: Estimated Cost; 2019-11-04: Current Cost; 2019-11-11: Cost Difference; 2019-11-18: Percentage Expenditure; 2019-12-09: 2020-01-13; 2019-12-16: 2020-01-20; 2019-12-23: 2020-01-27; 2019-12-30: 2020-02-03; 2020-01-06: 2020-02-10; 2020-01-13: 2020-02-17
| 1 | 2019-09-30: 16; 2019-10-07: 38; 2019-10-14: 22; 2019-10-21: 100%; 2019-10-28: 200; 2019-11-04: 475; 2019-11-11: 275; 2019-11-18: 238%; 2019-12-02: Daniel Bishop; 2019-12-16: 5; 2019-12-30: 4; 2020-01-20: 9; 2020-01-27: 15
| 2 | 2019-09-30: 8; 2019-10-07: 16; 2019-10-14: 8; 2019-10-21: 100%; 2019-10-28: 100; 2019-11-04: 200; 2019-11-11: 100; 2019-11-18: 200%; 2019-12-02: Oliver Clarke; 2020-01-20: 0; 2020-01-27: 75.25
| 5 | 2019-09-30: 4; 2019-10-07: 2; 2019-10-14: -2; 2019-10-21: 100%; 2019-10-28: 50; 2019-11-04: 25; 2019-11-11: -25; 2019-11-18: 50%; 2019-12-02: James Gardner; 2019-12-09: 1; 2019-12-16: 7; 2019-12-23: 12; 2019-12-30: 13; 2020-01-20: 33; 2020-01-27: 32.5
| 20 | 2019-09-30: 24; 2019-10-07: 6; 2019-10-14: -18; 2019-10-21: 100%; 2019-10-28: 300; 2019-11-04: 75; 2019-11-11: -225; 2019-11-18: 25%; 2019-12-02: Stijn Marynissen; 2020-01-20: 0; 2020-01-27: 44.25
[11 empty] | Che McKirgan |  | 5 | 6 | 9 |  |  | 20 | 26
[11 empty] | Cameron Smith | [6 empty] | 0 | 39.75
[11 empty] | Oliver Still | [6 empty] | 0 | 75.25
[11 empty] | Eric Walker | [6 empty] | 0 | 14.75
| Total: | 2019-09-30: 52; 2019-10-07: 62; 2019-10-14: 10; 2019-10-21: 100%; 2019-10-28: 650; 2019-11-04: 775; 2019-11-11: 125; 2019-11-18: 119%; 2020-01-13: Total Hours:; 2020-01-20: 62; 2020-01-27: 322.75
[17 empty] | Combined: | 384.75
[17 empty] | Current Cost | Budget | Remaining Budget
[17 empty] | 4809.38 | n/a | n/a
Iteration 1
| User Story | 2019-09-30: Estimated Hrs; 2019-10-07: Actual Hrs; 2019-10-14: Hrs Difference; 2019-10-21: Completion; 2019-10-28: Estimated Cost; 2019-11-04: Current Cost; 2019-11-11: Cost Difference; 2019-11-18: Percentage Expenditure; 2019-12-09: Week 7; 2019-12-16: Week 8; 2019-12-23: Week 9; 2019-12-30: Total Programming Hrs; 2020-01-06: Total Admin Hrs
| 3 | 2019-09-30: 4; 2019-10-07: 15; 2019-10-14: 11; 2019-10-21: 100%; 2019-10-28: 50; 2019-11-04: 187.5; 2019-11-11: 137.5; 2019-11-18: 375%; 2019-12-09: 2020-02-17; 2019-12-16: 2020-02-24; 2019-12-23: 2020-03-02
| 4 | 2019-09-30: 4; 2019-10-07: 8.25; 2019-10-14: 4.25; 2019-10-21: 100%; 2019-10-28: 50; 2019-11-04: 103.125; 2019-11-11: 53.125; 2019-11-18: 206.2%; 2019-12-02: Daniel Bishop; 2019-12-09: 3; 2019-12-16: 6.25; 2019-12-23: 0; 2019-12-30: 9.25; 2020-01-06: 2
| 8 | 2019-09-30: 8; 2019-10-07: 1.5; 2019-10-14: -6.5; 2019-10-21: 100%; 2019-10-28: 100; 2019-11-04: 18.75; 2019-11-11: -81.25; 2019-11-18: 18.75%; 2019-12-02: Oliver Clarke; 2019-12-09: 0; 2019-12-16: 3; 2019-12-23: 2.5; 2019-12-30: 5.5; 2020-01-06: 26
| 9 | 2019-09-30: 8; 2019-10-07: 2; 2019-10-14: -6; 2019-10-21: 100%; 2019-10-28: 100; 2019-11-04: 25; 2019-11-11: -75; 2019-11-18: 25%; 2019-12-02: James Gardner; 2019-12-09: 3; 2019-12-16: 10; 2019-12-23: 1; 2019-12-30: 14; 2020-01-06: 6.75
| 10 | 2019-09-30: 16; 2019-10-07: 13; 2019-10-14: -3; 2019-10-21: 67%; 2019-10-28: 200; 2019-11-04: 162.5; 2019-11-11: -37.5; 2019-11-18: 81.25%; 2019-12-02: Stijn Marynissen; 2019-12-09: 3; 2019-12-16: 4.25; 2019-12-23: 2; 2019-12-30: 9.25; 2020-01-06: 4
| 14 | 2019-09-30: 24; 2019-10-07: 10.5; 2019-10-14: -13.5; 2019-10-21: 70%; 2019-10-28: 300; 2019-11-04: 131.25; 2019-11-11: -168.75; 2019-11-18: 43.75%; 2019-12-02: Che McKirgan; 2019-12-09: 0; 2019-12-16: 4.5; 2019-12-23: 3; 2019-12-30: 7.5; 2020-01-06: 2
| 16 | 2019-09-30: 24; 2019-10-07: 18; 2019-10-14: -6; 2019-10-21: 100%; 2019-10-28: 300; 2019-11-04: 225; 2019-11-11: -75; 2019-11-18: 75%; 2019-12-02: Cameron Smith; 2019-12-09: 3; 2019-12-16: 2.25; 2019-12-23: 2.5; 2019-12-30: 7.75; 2020-01-06: 12
[11 empty] | Oliver Still | 3 | 4.75 | 2.5 | 10.25 | 15.75
| Total: | 2019-09-30: 88; 2019-10-07: 68.25; 2019-10-14: -19.75; 2019-10-21: 91%; 2019-10-28: 1100; 2019-11-04: 853.125; 2019-11-11: -246.875; 2019-11-18: 77.56%; 2019-12-02: Eric Walker; 2019-12-09: 3; 2019-12-16: 5.25; 2019-12-23: 0; 2019-12-30: 8.25; 2020-01-06: 3
[14 empty] | Total Hours: | 71.75 | 71.5
[14 empty] | Combined: | 143.25
[14 empty] | Current Cost | Budget | Remaining Budget
[14 empty] | 1790.63 | 1000 | -790.63
Iteration 2
| User Story | 2019-09-30: Estimated Hrs; 2019-10-07: Actual Hrs; 2019-10-14: Hrs Difference; 2019-10-21: Completion; 2019-10-28: Estimated Cost; 2019-11-04: Current Cost; 2019-11-11: Cost Difference; 2019-11-18: Percentage Expenditure; 2019-12-09: Week 9; 2019-12-16: Week 10; 2019-12-23: Break 1; 2019-12-30: Programming Hrs; 2020-01-06: Admin Hours Hrs
| 12 | 2019-09-30: 8; 2019-10-07: 0; 2019-10-14: -8; 2019-10-21: 0%; 2019-10-28: 100; 2019-11-04: £ -; 2019-11-11: -100; 2019-11-18: 0%; 2019-12-09: 2020-03-02; 2019-12-16: 2020-03-09; 2019-12-23: 2020-03-16
| 15 | 2019-09-30: 16; 2019-10-07: 0; 2019-10-14: -16; 2019-10-21: 0%; 2019-10-28: 200; 2019-11-04: £ -; 2019-11-11: -200; 2019-11-18: 0%; 2019-12-02: Daniel Bishop; 2019-12-09: 0; 2019-12-16: 0.75; 2019-12-23: 0; 2019-12-30: 0.75; 2020-01-06: 8
| 17 | 2019-09-30: 56; 2019-10-07: 14.5; 2019-10-14: -41.5; 2019-10-21: 30%; 2019-10-28: 700; 2019-11-04: 181.25; 2019-11-11: -518.75; 2019-11-18: 26%; 2019-12-02: Oliver Clarke; 2019-12-09: 0; 2019-12-16: 0; 2019-12-23: 4; 2019-12-30: 4; 2020-01-06: 12
| 10 (Overdue) | 2019-09-30: 3; 2019-10-07: 2; 2019-10-14: -1; 2019-10-21: 10%; 2019-10-28: 37.5; 2019-11-04: 25; 2019-11-11: -12.5; 2019-11-18: 67%; 2019-12-02: James Gardner; 2019-12-09: 0; 2019-12-16: 1; 2019-12-23: 4.75; 2019-12-30: 5.75; 2020-01-06: 14
| 14 (Overdue) | 2019-09-30: 13.5; 2019-10-07: 5; 2019-10-14: -8.5; 2019-10-21: 100%; 2019-10-28: 168.75; 2019-11-04: 62.5; 2019-11-11: -106.25; 2019-11-18: 37%; 2019-12-02: Stijn Marynissen; 2019-12-09: 0; 2019-12-16: 4.5; 2019-12-23: 5; 2019-12-30: 9.5; 2020-01-06: 2
| 31 (New) | 2019-09-30: 12; 2019-10-07: 11.75; 2019-10-14: -0.25; 2019-10-21: 100%; 2019-10-28: 150; 2019-11-04: 146.88; 2019-11-11: -3.13; 2019-11-18: 98%; 2019-12-02: Che McKirgan; 2019-12-09: 0; 2019-12-16: 5; 2019-12-23: 0; 2019-12-30: 5; 2020-01-06: 3
| 29 (New) | 2019-09-30: 24; 2019-10-07: 4; 2019-10-14: -20; 2019-10-21: 10%; 2019-10-28: 300; 2019-11-04: 50; 2019-11-11: -250; 2019-11-18: 17%; 2019-12-02: Cameron Smith; 2019-12-09: 0; 2019-12-16: 5.75; 2019-12-23: 0; 2019-12-30: 5.75; 2020-01-06: 18.5
| Total: | 2019-09-30: 132.5; 2019-10-07: 37.25; 2019-10-14: -95.25; 2019-10-21: 28%; 2019-10-28: 1656.25; 2019-11-04: 465.63; 2019-11-11: -1190.63; 2019-11-18: 28%; 2019-12-02: Oliver Still; 2019-12-09: 0; 2019-12-16: 8.25; 2019-12-23: 0.5; 2019-12-30: 8.75; 2020-01-06: 10
[11 empty] | Eric Walker | 0 | 0 | 2 | 2 | 10
[14 empty] | Total Hours: | 41.5 | 77.5
[14 empty] | Combined: | 119
[14 empty] | Current Cost | Budget | Remaining Budget
[14 empty] | 1487.5 | 950 | -537.5
Iteration 3 | bar: 2019-09-30 to 2019-11-18
| User Story | 2019-09-30: Estimated Hrs; 2019-10-07: Actual Hrs; 2019-10-14: Hrs Difference; 2019-10-21: Completion; 2019-10-28: Estimated Cost; 2019-11-04: Current Cost; 2019-11-11: Cost Difference; 2019-11-18: Percentage Expenditure; 2019-12-09: Break 1; 2019-12-16: Break 2; 2019-12-23: Break 3; 2019-12-30: Programming Hrs; 2020-01-06: Admin Hours Hrs
| 6 | 2019-09-30: 16; 2019-10-07: 7; 2019-10-14: -9; 2019-10-21: 100%; 2019-10-28: 200; 2019-11-04: 87.5; 2019-11-11: -112.5; 2019-11-18: 44%; 2019-12-09: 2020-03-16; 2019-12-16: 2020-03-23; 2019-12-23: 2020-03-30
| 7 | 2019-09-30: 8; 2019-10-07: 10; 2019-10-14: 2; 2019-10-21: 100%; 2019-10-28: 100; 2019-11-04: 125; 2019-11-11: 25; 2019-11-18: 125%; 2019-12-02: Daniel Bishop; 2019-12-09: 0; 2019-12-16: 6.5; 2019-12-23: 7.45; 2019-12-30: 13.95; 2020-01-06: 2.5
| 18 | 2019-09-30: 24; 2019-10-07: 11.25; 2019-10-14: -12.75; 2019-10-21: 100%; 2019-10-28: 300; 2019-11-04: 140.63; 2019-11-11: -159.38; 2019-11-18: 47%; 2019-12-02: Oliver Clarke; 2019-12-09: 0; 2019-12-16: 3; 2019-12-23: 4; 2019-12-30: 7; 2020-01-06: 9.5
| 19 | 2019-09-30: 24; 2019-10-07: 11.5; 2019-10-14: -12.5; 2019-10-21: 100%; 2019-10-28: 300; 2019-11-04: 143.75; 2019-11-11: -156.25; 2019-11-18: 48%; 2019-12-02: James Gardner; 2019-12-09: 0; 2019-12-16: 6.5; 2019-12-23: 7; 2019-12-30: 13.5; 2020-01-06: 5.5
| 10 (Overdue) | 2019-09-30: 1; 2019-10-07: 10.5; 2019-10-14: 9.5; 2019-10-21: 100%; 2019-10-28: 12.5; 2019-11-04: 131.25; 2019-11-11: 118.75; 2019-11-18: 1050%; 2019-12-02: Stijn Marynissen; 2019-12-09: 0; 2019-12-16: 4.5; 2019-12-23: 3; 2019-12-30: 7.5; 2020-01-06: 2.5
| 12 (Overdue) | 2019-09-30: 8; 2019-10-07: 7; 2019-10-14: -1; 2019-10-21: 100%; 2019-10-28: 100; 2019-11-04: 87.5; 2019-11-11: -12.5; 2019-11-18: 88%; 2019-12-02: Che McKirgan; 2019-12-09: 1; 2019-12-16: 2; 2019-12-23: 6; 2019-12-30: 9; 2020-01-06: 2
| 15 (Overdue) | 2019-09-30: 16; 2019-10-07: 10; 2019-10-14: -6; 2019-10-21: 100%; 2019-10-28: 200; 2019-11-04: 125; 2019-11-11: -75; 2019-11-18: 63%; 2019-12-02: Cameron Smith; 2019-12-09: 9; 2019-12-16: 9.75; 2019-12-23: 4; 2019-12-30: 22.75; 2020-01-06: 3.75
| 17 (Overdue) | 2019-09-30: 41.5; 2019-10-07: 7; 2019-10-14: -34.5; 2019-10-21: 80%; 2019-10-28: 518.75; 2019-11-04: 87.5; 2019-11-11: -431.25; 2019-11-18: 17%; 2019-12-02: Oliver Still; 2019-12-09: 0; 2019-12-16: 0; 2019-12-23: 1; 2019-12-30: 1; 2020-01-06: 8.75
| 29 (Overdue) | 2019-09-30: 20; 2019-10-07: 7; 2019-10-14: -13; 2019-10-21: 55%; 2019-10-28: 250; 2019-11-04: 87.5; 2019-11-11: -162.5; 2019-11-18: 35%; 2019-12-02: Eric Walker; 2019-12-09: 7.25; 2019-12-16: 9.75; 2019-12-23: 5.75; 2019-12-30: 22.75; 2020-01-06: 3
| 32 (New) | 2019-09-30: 16; 2019-10-07: 2; 2019-10-14: -14; 2019-10-21: 20%; 2019-10-28: 200; 2019-11-04: 25; 2019-11-11: -175; 2019-11-18: 13%; 2019-12-23: Total Hours:; 2019-12-30: 97.45; 2020-01-06: 37.5
| Total: | 2019-09-30: 174.5; 2019-10-07: 83.25; 2019-10-14: -91.25; 2019-10-21: 84%; 2019-10-28: 2181.25; 2019-11-04: 1040.63; 2019-11-11: -1140.63; 2019-11-18: 48%; 2019-12-23: Combined:; 2019-12-30: 134.95
[14 empty] | Current Cost | Budget | Remaining Budget
[14 empty] | 1686.88 | 900 | -786.88
Iteration 4 | bar: 2019-09-30 to 2019-11-18
| User Story | 2019-09-30: Estimated Hrs; 2019-10-07: Actual Hrs; 2019-10-14: Hrs Difference; 2019-10-21: Completion; 2019-10-28: Estimated Cost; 2019-11-04: Current Cost; 2019-11-11: Cost Difference; 2019-11-18: Percentage Expenditure; 2019-12-09: Break 3; 2019-12-16: Break 4; 2019-12-23: Week 1; 2019-12-30: Programming Hrs; 2020-01-06: Admin Hours Hrs
| 21 | 2019-09-30: 24; 2019-10-07: 9.25; 2019-10-14: -14.75; 2019-10-21: 100%; 2019-10-28: 300; 2019-11-04: 115.625; 2019-11-11: -184.375; 2019-11-18: 38.54%; 2019-12-09: 2020-03-30; 2019-12-16: 2020-04-06; 2019-12-23: 2020-04-13
| 22 | 2019-09-30: 16; 2019-10-07: 2; 2019-10-14: -14; 2019-10-21: 100%; 2019-10-28: 200; 2019-11-04: 25; 2019-11-11: -175; 2019-11-18: 12.5%; 2019-12-02: Daniel Bishop; 2019-12-09: 2; 2019-12-16: 16; 2019-12-23: 5.75; 2019-12-30: 23.75; 2020-01-06: 2.75
| 23 | 2019-09-30: 24; 2019-10-07: 16.25; 2019-10-14: -7.75; 2019-10-21: 50%; 2019-10-28: 300; 2019-11-04: 203.125; 2019-11-11: -96.875; 2019-11-18: 67.71%; 2019-12-02: Oliver Clarke; 2019-12-09: 2; 2019-12-16: 0; 2019-12-23: 8; 2019-12-30: 10; 2020-01-06: 10.25
| 27 | 2019-09-30: 8; 2019-10-07: 1; 2019-10-14: -7; 2019-10-21: 30%; 2019-10-28: 100; 2019-11-04: 12.5; 2019-11-11: -87.5; 2019-11-18: 12.5%; 2019-12-02: James Gardner; 2019-12-09: 13; 2019-12-16: 11; 2019-12-23: 3.5; 2019-12-30: 27.5; 2020-01-06: 4.75
| 28 | 2019-09-30: 4; 2019-10-07: 0; 2019-10-14: -4; 2019-10-21: 100%; 2019-10-28: 50; 2019-11-04: 0; 2019-11-11: -50; 2019-11-18: 0%; 2019-12-02: Stijn Marynissen; 2019-12-09: 3; 2019-12-16: 3; 2019-12-23: 5.25; 2019-12-30: 11.25; 2020-01-06: 3.35
| 17 (Overdue) | 2019-09-30: 34.5; 2019-10-07: 41.75; 2019-10-14: 7.25; 2019-10-21: 100%; 2019-10-28: 431.25; 2019-11-04: 521.875; 2019-11-11: 90.625; 2019-11-18: 121%; 2019-12-02: Che McKirgan; 2019-12-09: 0; 2019-12-16: 0; 2019-12-23: 11; 2019-12-30: 11; 2020-01-06: 3
| 29 (Overdue) | 2019-09-30: 13; 2019-10-07: 15; 2019-10-14: 2; 2019-10-21: 60%; 2019-10-28: 162.5; 2019-11-04: 187.5; 2019-11-11: 25; 2019-11-18: 115.4%; 2019-12-02: Cameron Smith; 2019-12-09: 0; 2019-12-16: 3; 2019-12-23: 0; 2019-12-30: 3; 2020-01-06: 2
| 32 (Overdue) | 2019-09-30: 14; 2019-10-07: 32.75; 2019-10-14: 18.75; 2019-10-21: 80%; 2019-10-28: 175; 2019-11-04: 409.375; 2019-11-11: 234.375; 2019-11-18: 233.9%; 2019-12-02: Oliver Still; 2019-12-09: 4.5; 2019-12-16: 3.25; 2019-12-23: 15.25; 2019-12-30: 23; 2020-01-06: 13.75
[11 empty] | Eric Walker | 0 | 12.5 | 5.75 | 18.25 | 7.5
| Total: | 2019-09-30: 137.5; 2019-10-07: 118; 2019-10-14: -19.5; 2019-10-21: 76%; 2019-10-28: 1718.75; 2019-11-04: 1475; 2019-11-11: -243.75; 2019-11-18: 85.82%; 2019-12-23: Total Hours:; 2019-12-30: 127.75; 2020-01-06: 47.35
[14 empty] | Combined: | 175.1
[14 empty] | Current Cost | Budget | Remaining Budget
[14 empty] | 2188.75 | 900 | -1288.75
Iteration 5 | bar: 2019-09-30 to 2019-11-18
| User Story | 2019-09-30: Estimated Hrs; 2019-10-07: Actual Hrs; 2019-10-14: Hrs Difference; 2019-10-21: Completion; 2019-10-28: Estimated Cost; 2019-11-04: Current Cost; 2019-11-11: Cost Difference; 2019-11-18: Percentage Expenditure; 2019-12-09: Week 1; 2019-12-16: Week 2; 2019-12-23: Week 3; 2019-12-30: Programming Hrs; 2020-01-06: Admin Hours Hrs
| 24 | 2019-09-30: 24; 2019-10-07: 0; 2019-10-14: -24; 2019-10-21: 80%; 2019-10-28: 300; 2019-11-04: 0; 2019-11-11: -300; 2019-11-18: 0%; 2019-12-09: 2020-04-13; 2019-12-16: 2020-04-20; 2019-12-23: 2020-04-27
| 25 | 2019-09-30: 32; 2019-10-07: 0; 2019-10-14: -32; 2019-10-21: 0%; 2019-10-28: 400; 2019-11-04: 0; 2019-11-11: -400; 2019-11-18: 0%; 2019-12-02: Daniel Bishop; 2019-12-09: 1.5; 2019-12-16: 9.75; 2019-12-23: 5.5; 2019-12-30: 16.75; 2020-01-06: 1.75
| 30 | 2019-09-30: 16; 2019-10-07: 0; 2019-10-14: -16; 2019-10-21: 100%; 2019-10-28: 200; 2019-11-04: 0; 2019-11-11: -200; 2019-11-18: 0%; 2019-12-02: Oliver Clarke; 2019-12-09: 4; 2019-12-16: 16.25; 2019-12-23: 5.5; 2019-12-30: 20.25; 2020-01-06: 10.25
| 23 (Overdue) | 2019-09-30: 7.75; 2019-10-07: 21; 2019-10-14: 13.25; 2019-10-21: 80%; 2019-10-28: 96.875; 2019-11-04: 262.5; 2019-11-11: 165.625; 2019-11-18: 271%; 2019-12-02: James Gardner; 2019-12-09: 0; 2019-12-16: 16; 2019-12-23: 1.5; 2019-12-30: 17.5; 2020-01-06: 4.5
| 27 (Overdue) | 2019-09-30: 7; 2019-10-07: 9.5; 2019-10-14: 2.5; 2019-10-21: 80%; 2019-10-28: 87.5; 2019-11-04: 118.75; 2019-11-11: 31.25; 2019-11-18: 135.7%; 2019-12-02: Stijn Marynissen; 2019-12-09: 0; 2019-12-16: 8.25; 2019-12-23: 2; 2019-12-30: 8.25; 2020-01-06: 3.75
| 29 (Overdue) | 2019-09-30: 0; 2019-10-07: 28; 2019-10-14: 28; 2019-10-21: 100%; 2019-10-28: 0; 2019-11-04: 350; 2019-11-11: 350; 2019-12-02: Che McKirgan; 2019-12-09: 0; 2019-12-16: 0; 2019-12-23: 0; 2019-12-30: 0; 2020-01-06: 2.75
| 32 (Overdue) | 2019-09-30: 0; 2019-10-07: 8; 2019-10-14: 8; 2019-10-21: 85%; 2019-10-28: 0; 2019-11-04: 100; 2019-11-11: 100; 2019-12-02: Cameron Smith; 2019-12-09: 0; 2019-12-16: 0; 2019-12-23: 0; 2019-12-30: 0; 2020-01-06: 38.25
| 03 (Updates) | 2019-09-30: 0; 2019-10-07: 18.75; 2019-10-14: 7.25; 2019-10-21: 60%; 2019-10-28: 0; 2019-11-04: 90.625; 2019-11-11: 90.625; 2019-12-02: Oliver Still; 2019-12-09: 0; 2019-12-16: 11.5; 2019-12-23: 8; 2019-12-30: 11.5; 2020-01-06: 18.75
| 04 (Updates) | 2019-09-30: 0; 2019-10-07: 1.5; 2019-10-14: 1.5; 2019-10-21: 100%; 2019-10-28: 0; 2019-11-04: 18.75; 2019-11-11: 18.75; 2019-12-02: Eric Walker; 2019-12-09: 0; 2019-12-16: 9.75; 2019-12-23: 5.5; 2019-12-30: 9.75; 2020-01-06: 7.25
| Total: | 2019-09-30: 86.75; 2019-10-07: 86.75; 2019-10-14: -11.5; 2019-10-21: 60%; 2019-10-28: 1084.375; 2019-11-04: 940.625; 2019-11-11: -143.75; 2019-11-18: 86.74%; 2019-12-23: Total Hours:; 2019-12-30: 84; 2020-01-06: 87.25
[14 empty] | Combined: | 171.25
[14 empty] | Current Cost | Budget | Remaining Budget
[14 empty] | 2140.63 | 900 | -1240.63
Iteration 6 | bar: 2019-09-30 to 2019-11-18
| User Story | 2019-09-30: Estimated Hrs; 2019-10-07: Actual Hrs; 2019-10-14: Hrs Difference; 2019-10-21: Completion; 2019-10-28: Estimated Cost; 2019-11-04: Current Cost; 2019-11-11: Cost Difference; 2019-11-18: Percentage Expenditure
| 11 | 2019-09-30: 8; 2019-10-07: 0; 2019-10-14: -8; 2019-10-21: 100%; 2019-10-28: 100; 2019-11-04: 0; 2019-11-11: -100; 2019-11-18: 0%
| 13 (Outsourced) | 2019-09-30: 24; 2019-10-07: 0; 2019-10-14: -24; 2019-10-21: 100%; 2019-10-28: 300; 2019-11-04: 0; 2019-11-11: -300; 2019-11-18: 0%
| 26 | 2019-09-30: 24; 2019-10-07: 0; 2019-10-14: -24; 2019-10-21: 100%; 2019-10-28: 300; 2019-11-04: 0; 2019-11-11: -300; 2019-11-18: 0%
| 29 | 2019-09-30: 24; 2019-10-07: 0; 2019-10-14: -24; 2019-10-21: 100%; 2019-10-28: 300; 2019-11-04: 0; 2019-11-11: -300; 2019-11-18: 0%
| 23 (Overdue) | 2019-09-30: 0; 2019-10-07: 0; 2019-10-14: 0; 2019-10-21: 0%; 2019-10-28: 0; 2019-11-04: 0; 2019-11-11: 0
| 25 (Overdue) | 2019-09-30: 32; 2019-10-07: 0; 2019-10-14: -32; 2019-10-21: 0%; 2019-10-28: 400; 2019-11-04: 0; 2019-11-11: -400; 2019-11-18: 0%
| 32 (Overdue) | 2019-09-30: 0; 2019-10-07: 0; 2019-10-14: 0; 2019-10-21: 0%; 2019-10-28: 0; 2019-11-04: 0; 2019-11-11: 0
| 03 (Updates) | 2019-09-30: 0; 2019-10-07: 0; 2019-10-14: 0; 2019-10-21: 60%; 2019-10-28: 0; 2019-11-04: 0; 2019-11-11: 0
| Total: | 2019-09-30: 112; 2019-10-07: 0; 2019-10-14: -112; 2019-10-21: 100%; 2019-10-28: 1400; 2019-11-04: 0; 2019-11-11: -1400; 2019-11-18: 0%