## User Stories
User Story ID | Estimated Days to Complete | Estimation in Hours |  | Programming Hours
1 | 2 | 16 | Total Hours From User Stories: | 548
2 | 1 | 8 | Hours Per Person: | 68.5
3 | 0.5 | 4 | Hours Per Iteration: | 78.2857
4 | 0.5 | 4 | Hours Per Person Per Iteration: | 9.7857
5 | 0.5 | 4
6 | 2 | 16
7 | 1 | 8
8 | 1 | 8
9 | 1 | 8
10 | 2 | 16
11 | 1 | 8
12 | 1 | 8
13 | 3 | 24
14 | 3 | 24
15 | 2 | 16
16 | 3 | 24
17 | 7 | 56
18 | 3 | 24
19 | 3 | 24
20 | 3 | 24
21 | 3 | 24
22 | 2 | 16
23 | 3 | 24
24 | 3 | 24
25 | 4 | 32
26 | 3 | 24
27 | 1 | 8
28 | 0.5 | 4
29 | 3 | 24
30 | 2 | 16
31 | 1.5 | 12
32 | 2 | 16
Total: | 68.5 | 548

## Overview
Iteration Expenditure Estimates
Iteration Period | User Stories | Estimated Total Hrs | Cost | Cost with Admin Hours (£) | Per Week Of Iteration (£)
Iteration 0 (16th Jan - 20th Feb) | 001, 002, 004, 020 | 52 | 650 | n/a | n/a
Iteration 1 (20th Feb - 5th Mar) | 003, 004, 008, 009, 010, 014, 016 | 88 | 1100 | 2000 | 1000
Iteration 2 (5th Mar - 19th Mar) | 012, 015, 017 | 80 | 1000 | 1900 | 950
Iteration 3 (19th Mar - 2nd Apr) | 006, 007, 018, 019 | 72 | 900 | 1800 | 900
Iteration 4 (2nd Apr - 16th Apr) | 021, 022, 023, 027, 028 | 76 | 950 | 1850 | 925
Iteration 5 (16th Apr - 30th Apr) | 024, 025, 030 | 72 | 900 | 1800 | 900
Iteration 6 (30th Apr - 14th May) | 011, 013, 026, 029 | 80 | 1000 | 1900 | 950
Iteration 7 (14th May - 28th May) | - | - | 900 | 1800 | 900
| Total: | 440 | 7400 | 13050
Iteration Actual Expenditure
Iteration Period | User Stories | Estimated Total Hrs | Extra Hours | Actual Hrs | Hrs Difference | Completion | Estimated Cost | Current Cost | Cost Difference | Percentage Expenditure | Iteration Cost | Iteration Budget | Remaining Iteration Budget | Notes
Iteration 0 (16th Jan - 20th Feb) | 001, 002, 004, 020 | 52 | 0 | 62 | 10 | 100% | 650 | 775 | 125 | 119.2% | 4809.375 | n/a | 0 | Iteration 0 is seen as a research & development stage. Was started before any budget had been made, hence no budget. Under-estimated programming time.
Iteration 1 (20th Feb - 5th Mar) | 003, 004, 008, 009, 010, 014, 016 | 88 | 0 | 68.25 | -19.75 | 91% | 1100 | 853.125 | -246.875 | 77.56% | 1790.625 | 2000 | 209.375 | Well within budget, however user stories have not been fully complete and are now passed into the next iteration. Completion - expenditure percentage ratio is good. Will have to be careful that user stories do not start to pile up between iterations.
Iteration 2 (5th Mar - 19th Mar) | 012, 015, 017, 010, 014, 029, 031 | 80 | 52.5 | 37.25 | -95.25 | 28% | 1000 | 465.625 | -534.375 | 46.56% | 1487.5 | 1900 | 412.5 | Included 2 new user stories (31 & 32) to for additional GUI elements, covered by the remaining budget from Iteration 1. Due to external deadlines (VHDL), compeltion is expected to be slightly under again.
Iteration 3 (19th Mar - 2nd Apr) | 006, 007, 018, 019, 010, 012, 015, 017, 029, 032 | 72 | 102.5 | 83.25 | -91.25 | 84% | 900 | 1040.625 | 140.625 | 115.6% | 1686.875 | 1800 | 113.125 | University course deadlines meant user stories were not complete. User stories increased from 4 to 10 and we completed 7 of them. This meant some followed through to iteration 4.
Iteration 4 (2nd Apr - 16th Apr) | 021, 022, 023, 027, 028, 017, 029, 032 | 76 | 61.5 | 118 | -19.5 | 76% | 950 | 1475 | 525 | 155.3% | 2188.75 | 1850 | -338.75 | Modules that utilised server handlers needed a second listener thread on the client side in order to effectively function. Thus, one was made half way in between the iteration and development on server modules were delayed.
Iteration 5 (16th Apr - 30th Apr) | 024, 025, 030, 023, 027, 029, 032, 004, 003 | 72 | 14.75 | 86.75 | 0 | 66.67% | 900 | 1084.375 | 184.375 | 120.5% | 2140.625 | 1800 | -340.625 | Big push to finish all overdue user stories and begin large merge for next iteration to produce full-featured program. Actual planned user stories mostly complete, apart from webcam which had no progress. O.S. made major updates to previous user stories 003 and 004.
Iteration 6 (30th Apr - 14th May) | 011, 013, 026, 029, 025, 032 | 80 | 32 | 25.5 | -86.5 | 100% | 1000 | 318.75 | -681.25 | 31.87% | 2081.25 | 1900 | -181.25 | All assigned user stories were completed as part of the functionality implemented in the previous iterations, leaving the only work to be updates or overdue stories. Story 13 was also outsourced.
Iteration 7 (14th May - 28th May) | 025, 030, 003 | 0 | 39 | 11 | -28 | 100% | 900 | 137.5 | -762.5 | 15.28% | 3134.375 | 1800 | -1334.375 | No assigned stories; iteration is used as a buffer to polish project and fix bugs.
| Total: | 628 |  | 492 | -330.25 | 80.71% | 7400 | 6150 | -1250 | 85.23% | 19319.375 | 13050 | -1460

## Iteration 0
User Story | Estimated Hrs | Actual Hrs | Hrs Difference | Completion | Estimated Cost | Current Cost | Cost Difference | Percentage Expenditure |  | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Programming Hrs | Admin Hours Hrs
1 | 16 | 38 | 22 | 100% | 200 | 475 | 275 | 237.5% |  | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17
2 | 8 | 16 | 8 | 100% | 100 | 200 | 100 | 200% | Daniel Bishop | 0 | 5 | 0 | 4 | 0 | 0 | 9 | 15
5 | 4 | 2 | -2 | 100% | 50 | 25 | -25 | 50% | Oliver Clarke | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.25
20 | 24 | 6 | -18 | 100% | 300 | 75 | -225 | 25% | James Gardner | 1 | 7 | 12 | 13 | 0 | 0 | 33 | 32.5
[9 empty] | Stijn Marynissen | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.25
[9 empty] | Che McKirgan | 0 | 5 | 6 | 9 | 0 | 0 | 20 | 26
[9 empty] | Cameron Smith | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.75
[9 empty] | Oliver Still | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.25
Total: | 52 | 62 | 10 | 100% | 650 | 775 | 125 | 119.2% | Eric Walker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.75
[10 empty] | 2020-02-17: Total Hours: | 62 | 322.75
[10 empty] | 2020-02-17: Combined: | 384.75
[10 empty] | 2020-02-17: Current Cost | Budget | Remaining Budget
[10 empty] | 2020-02-17: 4809.375 | n/a | n/a

## Iteration 1
User Story | Estimated Hrs | Actual Hrs | Hrs Difference | Completion | Estimated Cost | Current Cost | Cost Difference | Percentage Expenditure |  | Week 7 | Week 8 | Week 9 | Total Programming Hrs | Total Admin Hrs
3 | 4 | 15 | 11 | 100% | 50 | 187.5 | 137.5 | 375% |  | 2020-02-17 | 2020-02-24 | 2020-03-02
4 | 4 | 8.25 | 4.25 | 100% | 50 | 103.125 | 53.125 | 206.2% | Daniel Bishop | 3 | 6.25 | 0 | 9.25 | 2
8 | 8 | 1.5 | -6.5 | 100% | 100 | 18.75 | -81.25 | 18.75% | Oliver Clarke | 0 | 3 | 2.5 | 5.5 | 26
9 | 8 | 2 | -6 | 100% | 100 | 25 | -75 | 25% | James Gardner | 3 | 10 | 1 | 14 | 6.75
10 | 16 | 13 | -3 | 67% | 200 | 162.5 | -37.5 | 81.25% | Stijn Marynissen | 3 | 4.25 | 2 | 9.25 | 4
14 | 24 | 10.5 | -13.5 | 70% | 300 | 131.25 | -168.75 | 43.75% | Che McKirgan | 0 | 4.5 | 3 | 7.5 | 2
16 | 24 | 18 | -6 | 100% | 300 | 225 | -75 | 75% | Cameron Smith | 3 | 2.25 | 2.5 | 7.75 | 12
[9 empty] | Oliver Still | 3 | 4.75 | 2.5 | 10.25 | 15.75
Total: | 88 | 68.25 | -19.75 | 91% | 1100 | 853.125 | -246.875 | 77.56% | Eric Walker | 3 | 5.25 | 0 | 8.25 | 3
[12 empty] | Total Hours: | 71.75 | 71.5
[12 empty] | Combined: | 143.25
[12 empty] | Current Cost | Budget | Remaining Budget
[12 empty] | 1790.625 | 2000 | 209.375
Formulas:
Week 8 = [Week 7]+7

## Iteration 2
User Story | Estimated Hrs | Actual Hrs | Hrs Difference | Completion | Estimated Cost | Current Cost | Cost Difference | Percentage Expenditure |  | Week 9 | Week 10 | Break 1 | Programming Hrs | Admin Hours Hrs
12 | 8 | 0 | -8 | 0% | 100 | 0 | -100 | 0% |  | 2020-03-02 | 2020-03-09 | 2020-03-16
15 | 16 | 0 | -16 | 0% | 200 | 0 | -200 | 0% | Daniel Bishop | 0 | 0.75 | 0 | 0.75 | 8
17 | 56 | 14.5 | -41.5 | 30% | 700 | 181.25 | -518.75 | 25.89% | Oliver Clarke | 0 | 0 | 4 | 4 | 12
10 (Overdue) | 3 | 2 | -1 | 10% | 37.5 | 25 | -12.5 | 66.67% | James Gardner | 0 | 1 | 4.75 | 5.75 | 14
14 (Overdue) | 13.5 | 5 | -8.5 | 100% | 168.75 | 62.5 | -106.25 | 37.04% | Stijn Marynissen | 0 | 4.5 | 5 | 9.5 | 2
31 (New) | 12 | 11.75 | -0.25 | 100% | 150 | 146.875 | -3.125 | 97.92% | Che McKirgan | 0 | 5 | 0 | 5 | 3
29 (New) | 24 | 4 | -20 | 10% | 300 | 50 | -250 | 16.67% | Cameron Smith | 0 | 5.75 | 0 | 5.75 | 18.5
Total: | 132.5 | 37.25 | -95.25 | 28% | 1656.25 | 465.625 | -1190.625 | 28.11% | Oliver Still | 0 | 8.25 | 0.5 | 8.75 | 10
[9 empty] | Eric Walker | 0 | 0 | 2 | 2 | 10
[12 empty] | Total Hours: | 41.5 | 77.5
[12 empty] | Combined: | 119
[12 empty] | Current Cost | Budget | Remaining Budget
[12 empty] | 1487.5 | 1900 | 412.5
Formulas:
Week 10 = [Week 9]+7

## Iteration 3
User Story | Estimated Hrs | Actual Hrs | Hrs Difference | Completion | Estimated Cost | Current Cost | Cost Difference | Percentage Expenditure |  | Break 1 | Break 2 | Break 3 | Programming Hrs | Admin Hours Hrs
6 | 16 | 7 | -9 | 100% | 200 | 87.5 | -112.5 | 43.75% |  | 2020-03-16 | 2020-03-23 | 2020-03-30
7 | 8 | 10 | 2 | 100% | 100 | 125 | 25 | 125% | Daniel Bishop | 0 | 6.5 | 7.45 | 13.95 | 2.5
18 | 24 | 11.25 | -12.75 | 100% | 300 | 140.625 | -159.375 | 46.88% | Oliver Clarke | 0 | 3 | 4 | 7 | 9.5
19 | 24 | 11.5 | -12.5 | 100% | 300 | 143.75 | -156.25 | 47.92% | James Gardner | 0 | 6.5 | 7 | 13.5 | 5.5
10 (Overdue) | 1 | 10.5 | 9.5 | 100% | 12.5 | 131.25 | 118.75 | 1050% | Stijn Marynissen | 0 | 4.5 | 3 | 7.5 | 2.5
12 (Overdue) | 8 | 7 | -1 | 100% | 100 | 87.5 | -12.5 | 87.5% | Che McKirgan | 1 | 2 | 6 | 9 | 2
15 (Overdue) | 16 | 10 | -6 | 100% | 200 | 125 | -75 | 62.5% | Cameron Smith | 9 | 9.75 | 4 | 22.75 | 3.75
17 (Overdue) | 41.5 | 7 | -34.5 | 80% | 518.75 | 87.5 | -431.25 | 16.87% | Oliver Still | 0 | 0 | 1 | 1 | 8.75
29 (Overdue) | 20 | 7 | -13 | 55% | 250 | 87.5 | -162.5 | 35% | Eric Walker | 7.25 | 9.75 | 5.75 | 22.75 | 3
32 (New) | 16 | 2 | -14 | 20% | 200 | 25 | -175 | 12.5% |  |  |  | Total Hours: | 97.45 | 37.5
Total: | 174.5 | 83.25 | -91.25 | 84% | 2181.25 | 1040.625 | -1140.625 | 47.71% |  |  |  | Combined: | 134.95
[12 empty] | Current Cost | Budget | Remaining Budget
[12 empty] | 1686.875 | 1800 | 113.125
Formulas:
Break 2 = [Break 1]+7

## Iteration 4
User Story | Estimated Hrs | Actual Hrs | Hrs Difference | Completion | Estimated Cost | Current Cost | Cost Difference | Percentage Expenditure |  | Break 3 | Break 4 | Week 1 | Programming Hrs | Admin Hours Hrs
21 | 24 | 9.25 | -14.75 | 100% | 300 | 115.625 | -184.375 | 38.54% |  | 2020-03-30 | 2020-04-06 | 2020-04-13
22 | 16 | 2 | -14 | 100% | 200 | 25 | -175 | 12.5% | Daniel Bishop | 2 | 16 | 5.75 | 23.75 | 2.75
23 | 24 | 16.25 | -7.75 | 50% | 300 | 203.125 | -96.875 | 67.71% | Oliver Clarke | 2 | 0 | 8 | 10 | 10.25
27 | 8 | 1 | -7 | 30% | 100 | 12.5 | -87.5 | 12.5% | James Gardner | 13 | 11 | 3.5 | 27.5 | 4.75
28 | 4 | 0 | -4 | 100% | 50 | 0 | -50 | 0% | Stijn Marynissen | 3 | 3 | 5.25 | 11.25 | 3.35
17 (Overdue) | 34.5 | 41.75 | 7.25 | 100% | 431.25 | 521.875 | 90.625 | 121% | Che McKirgan | 0 | 0 | 11 | 11 | 3
29 (Overdue) | 13 | 15 | 2 | 60% | 162.5 | 187.5 | 25 | 115.4% | Cameron Smith | 0 | 3 | 0 | 3 | 2
32 (Overdue) | 14 | 32.75 | 18.75 | 80% | 175 | 409.375 | 234.375 | 233.9% | Oliver Still | 4.5 | 3.25 | 15.25 | 23 | 13.75
[9 empty] | Eric Walker | 0 | 12.5 | 5.75 | 18.25 | 7.5
Total: | 137.5 | 118 | -19.5 | 76% | 1718.75 | 1475 | -243.75 | 85.82% |  |  |  | Total Hours: | 127.75 | 47.35
[12 empty] | Combined: | 175.1
[12 empty] | Current Cost | Budget | Remaining Budget
[12 empty] | 2188.75 | 1850 | -338.75
Formulas:
Break 4 = [Break 3]+7

## Iteration 5
User Story | Estimated Hrs | Actual Hrs | Hrs Difference | Completion | Estimated Cost | Current Cost | Cost Difference | Percentage Expenditure |  | Week 1 | Week 2 | Week 3 | Programming Hrs | Admin Hours Hrs
24 | 24 | 0 | -24 | 100% | 300 | 0 | -300 | 0% |  | 2020-04-13 | 2020-04-20 | 2020-04-27
25 | 32 | 0 | -32 | 0% | 400 | 0 | -400 | 0% | Daniel Bishop | 1.5 | 9.75 | 5.5 | 16.75 | 1.75
30 | 16 | 0 | -16 | 100% | 200 | 0 | -200 | 0% | Oliver Clarke | 4 | 16.25 | 5.5 | 20.25 | 10.25
23 (Overdue) | 7.75 | 21 | 13.25 | 100% | 96.875 | 262.5 | 165.625 | 271% | James Gardner | 0 | 16 | 1.5 | 17.5 | 4.5
27 (Overdue) | 7 | 9.5 | 2.5 | 80% | 87.5 | 118.75 | 31.25 | 135.7% | Stijn Marynissen | 0 | 8.25 | 2 | 8.25 | 3.75
29 (Overdue) | 0 | 28 | 28 | 100% | 0 | 350 | 350 |  | Che McKirgan | 0 | 0 | 0 | 0 | 2.75
32 (Overdue) | 0 | 8 | 8 | 85% | 0 | 100 | 100 |  | Cameron Smith | 0 | 0 | 0 | 0 | 38.25
03 (Updates) | 0 | 18.75 | 7.25 | 60% | 0 | 90.625 | 90.625 |  | Oliver Still | 0 | 11.5 | 8 | 11.5 | 18.75
04 (Updates) | 0 | 1.5 | 1.5 | 100% | 0 | 18.75 | 18.75 |  | Eric Walker | 0 | 9.75 | 5.5 | 9.75 | 7.25
Total: | 86.75 | 86.75 | -11.5 | 66.67% | 1084.375 | 940.625 | -143.75 | 86.74% |  |  |  | Total Hours: | 84 | 87.25
[12 empty] | Combined: | 171.25
[12 empty] | Current Cost | Budget | Remaining Budget
[12 empty] | 2140.625 | 1800 | -340.625
Formulas:
Week 2 = [Week 1]+7

## Iteration 6
User Story | Estimated Hrs | Actual Hrs | Hrs Difference | Completion | Estimated Cost | Current Cost | Cost Difference | Percentage Expenditure |  | Week 3 | Week 4 | Week 5 | Programming Hrs | Admin Hours Hrs
11 | 8 | 0 | -8 | 100% | 100 | 0 | -100 | 0% |  | 2020-04-27 | 2020-05-04 | 2020-05-11
13 (Outsourced) | 24 | 0 | -24 | 100% | 300 | 0 | -300 | 0% | Daniel Bishop | 0 | 0 | 0 | 0 | 7.75
26 | 24 | 0 | -24 | 100% | 300 | 0 | -300 | 0% | Oliver Clarke | 1.5 | 0 | 0 | 1.5 | 13
29 | 24 | 0 | -24 | 100% | 300 | 0 | -300 | 0% | James Gardner | 6 | 7 | 5.25 | 18.25 | 7.5
25 (Overdue) | 32 | 13 | -19 | 60% | 400 | 162.5 | -237.5 | 40.62% | Stijn Marynissen | 4 | 3.5 | 0 | 7.5 | 2
32 (Overdue) | 0 | 4 | 4 | 100% | 0 | 50 | 50 |  | Che McKirgan | 0 | 10 | 8 | 18 | 13.25
03 (Updates) | 0 | 6 | 0 | 60% | 0 | 75 | 75 |  | Cameron Smith | 0 | 0 | 0 | 0 | 28.5
06 (Updates) | 0 | 2.5 | 2.5 | 100% | 0 | 31.25 | 31.25 |  | Oliver Still | 8.75 | 0 | 1 | 9.75 | 23
[9 empty] | Eric Walker | 0 | 5.25 | 3.25 | 8.5 | 8
Total: | 112 | 25.5 | -92.5 | 100% | 1300 | 318.75 | -981.25 | 24.52% |  |  |  | Total Hours: | 63.5 | 103
[12 empty] | Combined: | 166.5
[12 empty] | Current Cost | Budget | Remaining Budget
[12 empty] | 2081.25 | 1900 | -181.25
Formulas:
Week 4 = [Week 3]+7

## Iteration 7
User Story | Estimated Hrs | Actual Hrs | Hrs Difference | Completion | Estimated Cost | Current Cost | Cost Difference | Percentage Expenditure |  | Week 5 | Week 6 | Week 7 | Programming Hrs | Admin Hours Hrs
25 (Overdue) | 19 | 5 | -14 | 90% | 237.5 | 62.5 | -175 | 26.32% |  | 2020-05-11 | 2020-05-18 | 2020-05-25
30 (Overdue) | 0 |  | 0 |  | 0 | 0 | 0 |  | Daniel Bishop | 0 | 0 | 0 | 0 | 1.25
03 (Updates) | 0 | 6 | 6 | 100% | 0 | 75 | 75 |  | Oliver Clarke | 0 | 0 | 0 | 0 | 49.5
[9 empty] | James Gardner | 0 | 22.5 | 13.75 | 36.25 | 11.75
[9 empty] | Stijn Marynissen | 0 | 1 | 0 | 1 | 4.25
[9 empty] | Che McKirgan | 5 | 9 | 13 | 27 | 1.75
[9 empty] | Cameron Smith | 0 | 0 | 0 | 0 | 68.5
[9 empty] | Oliver Still | 0 | 7 | 0 | 7 | 30.25
Total: | 19 | 11 | -8 | 100% | 237.5 | 137.5 | -100 | 57.89% | Eric Walker | 0 | 7 | 0 | 7 | 5.25
[12 empty] | Total Hours: | 78.25 | 172.5
[12 empty] | Combined: | 250.75
[12 empty] | Current Cost | Budget | Remaining Budget
[12 empty] | 3134.375 | 1800 | -1334.375
Formulas:
Week 6 = [Week 5]+7